## Data Rights Notice
PROTECTED RIGHTS NOTICE
These protected data were produced under agreement no. DE-EE0007347 with the U.S. Department of Energy and may not be published, disseminated, or disclosed to others outside the Government until five (5) years from the date the data were first produced, unless express written authorization is obtained from the recipient. Upon expiration of the period of protection set forth in this Notice, the Government shall have unlimited rights in this data. This Notice shall be marked on any reproduction of this data, in whole or in part.

## 0630 Hull Penetrations
[13 empty] | Risk Ranking | [11 empty] | Updated Risk Ranking | [11 empty] | 2nd Updated Risk Ranking
0630 Hull Penetrations FMECA Table | [13 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Recommended Actions | Responsible Party | Actions Taken | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | 2nd Recommended Actions | Responsible Party (2nd) | Actions Taken (2nd) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Status (open or closed) | Notes
0630-1 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Minor Leak in hatch or cable penetration seal | 1) Water intrusion | Fatigue crack in seal | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 7 | 1 | 1 | 3 | 4 | Low | Low | Low | Low
0630-2 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Minor Leak in hatch or cable penetration seal | 1) Water intrusion | Damage from debris | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 7 | 1 | 1 | 3 | 4 | Low | Low | Low | Low | 1. Design of the seals to take into account higher level of contamination. Sufficient wear allowance between maintenance intervals shall be demonstrated. The level of contamination shall be compatible with the expected debris 2. CP to define a debris management plan, including but not limited to the follow aspects: a. Define the acceptance criteria for debris b. Debris identification and management. c. Design of diversion features for debris of unacceptable size, or design to reduce the impact on air gap due to the presence of debris. d. Design features to reduce the part count per unit volume of debris. CP to document the management plan, demonstrating the measures are being implemented in design, manufacturing and operational stages.
0630-3 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Minor Leak in hatch or cable penetration seal | 1) Water intrusion | Overpressurization | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 6 | 1 | 1 | 3 | 4 | Low | Low | Low | Low | [25 empty] | DNV GL comment: Please explain the scenario during which overpressurization will occur.
0630-4 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Minor Leak in hatch or cable penetration seal | 1) Water intrusion | Deformation of mating structure | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 7 | 1 | 1 | 3 | 4 | Low | Low | Low | Low | FEA to show structural rigidity around hatch interface. Structural reinforcement to be added where needed
0630-5 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Major Leak in hatch or cable penetration seal | 1) Water intrusion 2) Component damage from corrosion | Fatigue crack in seal | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 6 | 1 | 1 | 7 | 7 | Low | Low | Med | Med | 1) Standard hull/bulkhead penetrations and approved fittings/hatches should be used. 2) Leak testing of watertight compartments before deployment 3) In-service inspection for damage, visible leakage of penetrations.
0630-6 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Major Leak in hatch or cable penetration seal | 1) Water intrusion 2) Component damage from corrosion | Damage from debris | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 6 | 1 | 1 | 7 | 7 | Low | Low | Med | Med | 1. Design of the seals to take into account higher level of contamination. Sufficient wear allowance between maintenance intervals shall be demonstrated. The level of contamination shall be compatible with the expected debris 2. CP to define a debris management plan, including but not limited to the follow aspects: a. Define the acceptance criteria for debris b. Debris identification and management. c. Design of diversion features for debris of unacceptable size, or design to reduce the impact on air gap due to the presence of debris. d. Design features to reduce the part count per unit volume of debris. CP to document the management plan, demonstrating the measures are being implemented in design, manufacturing and operational stages.
0630-7 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Major Leak in hatch or cable penetration seal | 1) Water intrusion 2) Component damage from corrosion | Overpressurization | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 5 | 1 | 1 | 7 | 7 | Low | Low | Med | Med | [25 empty] | DNV GL comment: Please explain the scenario during which overpressurization will occur.
0630-8 | Hull Penetrations | Hatches and cable penetrations | 2 |  | Major Leak in hatch or cable penetration seal | 1) Water intrusion 2) Component damage from corrosion | Deformation of mating structure | Normal | All hatches and cable penetrations are placed above the mean waterline. All hatches and cable penetrations are on the nacelle platforms which are 5.7m above the waterline except for the emergency hatches. All compartments have two bilge pumps | None | Bilge detection | Repair seal on site | 6 | 1 | 1 | 7 | 7 | Low | Low | Med | Med | 1) Approved standard hatches should be used. 2) Leak testing before deployment 3) In-service inspection for damage, visible leakage of penetrations. 4) FEA to show structural rigidity around hatch interface. Structural reinforcement to be added where needed

## version history
Title | StingRAY Hull Penetrations FMECA
Doc No | SR-0630-RR
Version | 3.6
Authored | E Hammagren
Reviewed
Approved Dist.
Approved Final
Version | Date | Summary
1.0 | 2016-02-01 | release to RC for review
3.0 | 2016-07-25 | Updated risk matrix, updated for WEC v3.3 technology (DNV GL comments incorporated)
3.6 | 2018-06-05 | updated for 7347 WBS 14 BP2 (updates from RC comments not in BP1 RR)
The following contains PROTECTED DATA of Columbia Power Technologies, Inc. not for distribution.

## set up
| Risk = Occ + Sev | [11 empty] | Note:
| Severity | [11 empty] | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
10 | Low | Med | Med | Med | Med | High | High | High | High | High
9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11
8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15
7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High
6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High
5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med
4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med |  | Low | Tolerable, no engineer action required
3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med |  | Med | Undesirable, consider engineer actions to mitigate risk
2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med |  | High | Intolerable, engineering action required
1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low
Occurrence | [5 empty] | Severity
Rating | Occurrence |  | Annual Failure Rate | Return Period [years] |  | Rating | Severity | Human Safety |  | Environment |  | WEC Operation |  | Assets
1 | Exceptionally unlikely to occur |  | 1e-05 | 100000 |  | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) |  | Negligible pollution or no effect on environment |  | Negligible effect on performance |  | Negligible
2 |  |  | 3.1623e-05 | 31600 |  | 2 | [7 empty] | [1.5k USD]
3 | Extremely unlikely to occur |  | 0.0001 | 10000 |  | 3 | Minor | Minor injuries, health effects (e.g. stitches) |  | Minor pollution / slight effect on environment (min disruption on marine life) |  | Minor system degradation |  | Repairable in-situ, at next maintenance interval [5k USD]
4 |  |  | 0.00031623 | 3160 |  | 4 |  | Moderate injuries and/or health effects (e.g. broken bone) |  |  |  | Moderate system degradation (e.g. loss of MoMo) |  | Repairable in-situ, outside maintenance interval (1 day) [15k USD]
5 | Very unlikely to occur |  | 0.001 | 1000 |  | 5 | Major |  |  | Limited levels of pollution, manageable / moderate effect on environment |  |  |  | Repairable in-situ, outside maintenance interval (1 week) [50k USD]
6 |  |  | 0.0031623 | 316 |  | 6 | [5 empty] | Major system degradation or loss of operation for 1 month |  | [150k USD]
7 | Rarely expected to occur |  | 0.01 | 100 |  | 7 | Critical | Hospitalization (with full recovery) |  | Moderate pollution (some clean-up costs) / Serious effect on environment |  | Major system degradation or loss of operation for 3 months |  | Dry dock required for repair [500k USD]
8 |  |  | 0.031623 | 31.6 |  | 8 | [5 empty] | Critical system degradation or loss of operation for 6 months |  | [1.5M USD]
9 | One or more during 20 yr lifetime |  | 0.1 | 10 |  | 9 | Catastrophic | Hospitalization (with lasting disabilities) |  | Major pollution (significant clean-up costs) / disastrous effects on the environment |  | Failure to generate power for remainder of project, complete failure |  | Loss of device [5M USD]
10 |  |  | 0.31623 | 3.16 |  | 10 |  | A fatality

## linkedPage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | Risk = Occ + Sev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note:
0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
0 | Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
0 | 10 | Low | Med | Med | Med | Med | High | High | High | High | High | 0 | 0 | 0 | 0 | 0
0 | 9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11 | 0 | 0 | 0
0 | 8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15 | 0 | 0 | 0
0 | 7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High | 0 | 0 | 0 | 0 | 0
0 | 6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High | 0 | 0 | 0 | 0 | 0
0 | 5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med | 0 | 0 | 0 | 0 | 0
0 | 4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med | 0 | Low | Tolerable, no engineer action required | 0 | 0
0 | 3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med | 0 | Med | Undesirable, consider engineer actions to mitigate risk | 0 | 0
0 | 2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med | 0 | High | Intolerable, engineering action required | 0 | 0
0 | 1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Occurrence | 0 | 0 | 0 | 0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Rating | Occurrence | 0 | Annual Failure Rate | Return Period [years] | 0 | Rating | Severity | Human Safety | 0 | Environment | 0 | WEC Operation | 0 | Assets | 0
0 | 1 | Exceptionally unlikely to occur | 0 | 1e-05 | 100000 | 0 | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) | 0 | Negligible pollution or no effect on environment | 0 | Negligible effect on performance | 0 | Negligible | 0
0 | 2 | 0 | 0 | 3.1623e-05 | 31600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [1.5k USD] | 0
0 | 3 | Extremely unlikely to occur | 0 | 0.0001 | 10000 | 0 | 3 | Minor | Minor injuries, health effects (e.g. stitches) | 0 | Minor pollution / slight effect on environment (min disruption on marine life) | 0 | Minor system degradation | 0 | Repairable in-situ, at next maintenance interval [5k USD] | 0
0 | 4 | 0 | 0 | 0.00031623 | 3160 | 0 | 4 | 0 | Moderate injuries and/or health effects (e.g. broken bone) | 0 | 0 | 0 | Moderate system degradation (e.g. loss of MoMo) | 0 | Repairable in-situ, outside maintenance interval (1 day) [15k USD] | 0
0 | 5 | Very unlikely to occur | 0 | 0.001 | 1000 | 0 | 5 | Major | 0 | 0 | Limited levels of pollution, manageable / moderate effect on environment | 0 | 0 | 0 | Repairable in-situ, outside maintenance interval (1 week) [50k USD] | 0
0 | 6 | 0 | 0 | 0.0031623 | 316 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Major system degradation or loss of operation for 1 month | 0 | [150k USD] | 0
0 | 7 | Rarely expected to occur | 0 | 0.01 | 100 | 0 | 7 | Critical | Hospitalization (with full recovery) | 0 | Moderate pollution (some clean-up costs) / Serious effect on environment | 0 | Major system degradation or loss of operation for 3 months | 0 | Dry dock required for repair [500k USD] | 0
0 | 8 | 0 | 0 | 0.031623 | 31.6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | Critical system degradation or loss of operation for 6 months | 0 | [1.5M USD] | 0
0 | 9 | One or more during 20 yr lifetime | 0 | 0.1 | 10 | 0 | 9 | Catastrophic | Hospitalization (with lasting disabilities) | 0 | Major pollution (significant clean-up costs) / disastrous effects on the environment | 0 | Failure to generate power for remainder of project, complete failure | 0 | Loss of device [5M USD] | 0
0 | 10 | 0 | 0 | 0.31623 | 3.16 | 0 | 10 | 0 | A fatality | 0 | 0 | 0 | 0 | 0 | 0 | 0