## Data Rights Notice
PROTECTED RIGHTS NOTICE
These protected data were produced under agreement no. DE-EE0007347 with the U.S. Department of Energy and may not be published, disseminated, or disclosed to others outside the Government until five (5) years from the date the data were first produced, unless express written authorization is obtained from the recipient. Upon expiration of the period of protection set forth in this Notice, the Government shall have unlimited rights in this data. This Notice shall be marked on any reproduction of this data, in whole or in part.

## 1100 Operations
[13 empty] | Risk Ranking | [11 empty] | Updated Risk Ranking | [11 empty] | 2nd Updated Risk Ranking
1100 Installation, Operations & Recovery FMECA Table | [13 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Recommended Actions | Responsible Party | Actions Taken | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | 2nd Recommended Actions | Responsible Party (2nd) | Actions Taken (2nd) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Status (open or closed) | Notes
1100-1 | Mooring system | Keep WEC on station and properly oriented |  |  | Tow line failure | 1) Loss of control of WEC position/motion | Extreme load | Transit | Proper line/component sizing | none | 1) Visual detection | Repair/replace on site | 3 | 7 | 1 | 4 | 5 | Low | Low | Low | Low | none
1100-2 | Mooring system | Keep WEC on station and properly oriented |  |  | Tow line failure | 1) Loss of control of WEC position/motion | Extreme load | Installation | Proper line/component sizing | none | 1) Visual detection | Repair/replace on site | 3 | 7 | 1 | 4 | 5 | Low | Low | Low | Low | none
1100-3 | Mooring system | Keep WEC on station and properly oriented |  |  | Tow line failure | 1) Loss of control of WEC position/motion | Extreme load | Removal | Proper line/component sizing | none | 1) Visual detection | Repair/replace on site | 4 | 7 | 1 | 4 | 5 | Low | Low | Low | Low | none
1100-4 | Barge | Support WEC during transit |  |  | WEC fatigue | 1) pre-deployment damage | fatigue load during transit | Transit | Conservative blocking and tie-down | 1) Visual inspection during transit | 1) Visual detection | Repair/replace in harbor | 6 | 7 | 1 | 6 | 6 | Med | Low | Med | Med | none | [24 empty] | Support of AFT fixed float?
1100-5 | Operations schedule | Plan project |  |  | Inclement weather | Project delay | Weather forecast | all | use forecast and past history | none | 1) observed | wait in harbor | 9 | 1 | 1 | 5 | 6 | Low | Low | Med | Med | [25 empty] | occurrence rate reduced from 1 in 3 years, to 1 in 10 years… 1 in 3 was too high
0110-12 0120-12 | Forward float Aft float | Wave activated body | 2 | Loading | fore/aft float breaks off under tow | 1) Wave loading of float is no longer transferred to rotor 2) Loss of power production 3) BOB/BOTS | High tow loads | Transport | Large partial safety factor on tow loads | 1) load cells on tow lines 2) slow down! | visual | 1) Recover float immediatly 2) drydock reatachment if possible | 3 | 2 | 1 | 6 | 6 | Low | Low | Low | Low | [25 empty] | Tow lines no longer connect to floats
1115.2-1 | External buoyancy module | Provide additional buoyancy to lower part of WEC, facilitating transition from vertical to horizontal configuration | 2 | Loading, dynamic attachment / detachment | Unexpected buoyncy module detachment | 1) Rapid transition from tow horizontal tow configuration to vertical 2) Potential for structural damage in shallow locations | External buoyancy modules break free of WEC during tow operation (or become flooded) | Transit - Towing | none | none | Visual detection | - If no impact with sea floor: transition back to tow config, secure buoyancy modules, continue with tow - If yes impact with sea floor: transition back to tow config, secure buoyancy modules, tow to harbor / dry dock for inspection and repair | 7 | 3 | 3 | 7 | 7 | Low | Low | Med | Med | Redesign hull to allow horizontal tow configuration using only hull buoyancy (no external modules) | PLB | - H2 hull design (conceptual, but design by Ershigs underway as of 2/24/17) (design being finalized by Glosten) allows for ascent / descent / towing all without external ballast tanks - severity classes unchanged, but occurrence reduced to 1 as buoyancy modules cannot break free (severity classes reduced because this is no longer possible) | 1 | 3 | 3 | 3 | 3 | Low | Low | Low | Low | [13 empty] | occurrence rate assumes 2% chance of failure, and 2x towing every 5 years
1115.2-2 | External buoyancy module | Provide additional buoyancy to lower part of WEC, facilitating transition from vertical to horizontal configuration | 2 | Loading, dynamic attachment / detachment | Failure to attach or detach modules in dynamic environment | 1) Delay of schedule while waiting for very calm conditions 2) Worst case scenario… unable to retrieve damaged / flooding WEC in time, leading to sinking | Metocean conditions (waves) render it difficult / impossible to attach external buoyancy modules | Emergency | none | none | Visual detection | WEC salvage operation (assumes WEC sinks) | 5 | 1 | 7 | 9 | 9 | Low | Med | Med | Med | Redesign hull to allow horizontal tow configuration using only hull buoyancy (no external modules) | PLB | - H2 hull design (conceptual, but design by Ershigs underway as of 2/24/17) (design being finalized by Glosten) allows for ascent / descent / towing all without external ballast tanks - severity classes unchanged, but occurrence reduced to 1 as buoyancy modules cannot break free (severity classes reduced because this is no longer possible) | 1 | 1 | 3 | 3 | 3 | Low | Low | Low | Low | [13 empty] | risk ranking assumes worst possible scenario (impossible to retrieve WEC during emergency)

## version history
Title | StingRAY Operations FMECA
Doc No | SR-1100-RR
Version | 3.6
Authored
Reviewed
Approved Dist.
Approved Final
Version | Date | Summary
3.0 | 2016-07-25 | Updated risk matrix, updated for WEC v3.3 technology
3.6 | 2018-06-05 | reviewed for 7347 WBS 14 BP2 (minor changes)
The following contains PROTECTED DATA of Columbia Power Technologies, Inc. not for distribution.

## set up
| Risk = Occ + Sev | [11 empty] | Note:
| Severity | [11 empty] | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
10 | Low | Med | Med | Med | Med | High | High | High | High | High
9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11
8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15
7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High
6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High
5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med
4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med |  | Low | Tolerable, no engineer action required
3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med |  | Med | Undesirable, consider engineer actions to mitigate risk
2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med |  | High | Intolerable, engineering action required
1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low
Occurrence | [5 empty] | Severity
Rating | Occurrence |  | Annual Failure Rate | Return Period [years] |  | Rating | Severity | Human Safety |  | Environment |  | WEC Operation |  | Assets
1 | Exceptionally unlikely to occur |  | 1e-05 | 100000 |  | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) |  | Negligible pollution or no effect on environment |  | Negligible effect on performance |  | Negligible
2 |  |  | 3.1623e-05 | 31600 |  | 2 | [7 empty] | [1.5k USD]
3 | Extremely unlikely to occur |  | 0.0001 | 10000 |  | 3 | Minor | Minor injuries, health effects (e.g. stitches) |  | Minor pollution / slight effect on environment (min disruption on marine life) |  | Minor system degradation |  | Repairable in-situ, at next maintenance interval [5k USD]
4 |  |  | 0.00031623 | 3160 |  | 4 |  | Moderate injuries and/or health effects (e.g. broken bone) |  |  |  | Moderate system degradation (e.g. loss of MoMo) |  | Repairable in-situ, outside maintenance interval (1 day) [15k USD]
5 | Very unlikely to occur |  | 0.001 | 1000 |  | 5 | Major |  |  | Limited levels of pollution, manageable / moderate effect on environment |  |  |  | Repairable in-situ, outside maintenance interval (1 week) [50k USD]
6 |  |  | 0.0031623 | 316 |  | 6 | [5 empty] | Major system degradation or loss of operation for 1 month |  | [150k USD]
7 | Rarely expected to occur |  | 0.01 | 100 |  | 7 | Critical | Hospitalization (with full recovery) |  | Moderate pollution (some clean-up costs) / Serious effect on environment |  | Major system degradation or loss of operation for 3 months |  | Dry dock required for repair [500k USD]
8 |  |  | 0.031623 | 31.6 |  | 8 | [5 empty] | Critical system degradation or loss of operation for 6 months |  | [1.5M USD]
9 | One or more during 20 yr lifetime |  | 0.1 | 10 |  | 9 | Catastrophic | Hospitalization (with lasting disabilities) |  | Major pollution (significant clean-up costs) / disastrous effects on the environment |  | Failure to generate power for remainder of project, complete failure |  | Loss of device [5M USD]
10 |  |  | 0.31623 | 3.16 |  | 10 |  | A fatality

## linkedPage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | Risk = Occ + Sev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note:
0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
0 | Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
0 | 10 | Low | Med | Med | Med | Med | High | High | High | High | High | 0 | 0 | 0 | 0 | 0
0 | 9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11 | 0 | 0 | 0
0 | 8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15 | 0 | 0 | 0
0 | 7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High | 0 | 0 | 0 | 0 | 0
0 | 6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High | 0 | 0 | 0 | 0 | 0
0 | 5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med | 0 | 0 | 0 | 0 | 0
0 | 4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med | 0 | Low | Tolerable, no engineer action required | 0 | 0
0 | 3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med | 0 | Med | Undesirable, consider engineer actions to mitigate risk | 0 | 0
0 | 2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med | 0 | High | Intolerable, engineering action required | 0 | 0
0 | 1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Occurrence | 0 | 0 | 0 | 0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Rating | Occurrence | 0 | Annual Failure Rate | Return Period [years] | 0 | Rating | Severity | Human Safety | 0 | Environment | 0 | WEC Operation | 0 | Assets | 0
0 | 1 | Exceptionally unlikely to occur | 0 | 1e-05 | 100000 | 0 | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) | 0 | Negligible pollution or no effect on environment | 0 | Negligible effect on performance | 0 | Negligible | 0
0 | 2 | 0 | 0 | 3.1623e-05 | 31600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [1.5k USD] | 0
0 | 3 | Extremely unlikely to occur | 0 | 0.0001 | 10000 | 0 | 3 | Minor | Minor injuries, health effects (e.g. stitches) | 0 | Minor pollution / slight effect on environment (min disruption on marine life) | 0 | Minor system degradation | 0 | Repairable in-situ, at next maintenance interval [5k USD] | 0
0 | 4 | 0 | 0 | 0.00031623 | 3160 | 0 | 4 | 0 | Moderate injuries and/or health effects (e.g. broken bone) | 0 | 0 | 0 | Moderate system degradation (e.g. loss of MoMo) | 0 | Repairable in-situ, outside maintenance interval (1 day) [15k USD] | 0
0 | 5 | Very unlikely to occur | 0 | 0.001 | 1000 | 0 | 5 | Major | 0 | 0 | Limited levels of pollution, manageable / moderate effect on environment | 0 | 0 | 0 | Repairable in-situ, outside maintenance interval (1 week) [50k USD] | 0
0 | 6 | 0 | 0 | 0.0031623 | 316 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Major system degradation or loss of operation for 1 month | 0 | [150k USD] | 0
0 | 7 | Rarely expected to occur | 0 | 0.01 | 100 | 0 | 7 | Critical | Hospitalization (with full recovery) | 0 | Moderate pollution (some clean-up costs) / Serious effect on environment | 0 | Major system degradation or loss of operation for 3 months | 0 | Dry dock required for repair [500k USD] | 0
0 | 8 | 0 | 0 | 0.031623 | 31.6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | Critical system degradation or loss of operation for 6 months | 0 | [1.5M USD] | 0
0 | 9 | One or more during 20 yr lifetime | 0 | 0.1 | 10 | 0 | 9 | Catastrophic | Hospitalization (with lasting disabilities) | 0 | Major pollution (significant clean-up costs) / disastrous effects on the environment | 0 | Failure to generate power for remainder of project, complete failure | 0 | Loss of device [5M USD] | 0
0 | 10 | 0 | 0 | 0.31623 | 3.16 | 0 | 10 | 0 | A fatality | 0 | 0 | 0 | 0 | 0 | 0 | 0