## SunkFloatStrategy RiskAnalysis
|  |  |  | 0-5 | 0-5 | 0-5 | 0-5 | 0-5 | 0-5 | 0-5 | 0-5 | 0-25 | 0-25 | 0-25 | 0-25 | 0-25 | 0-25 | 0-25
|  |  |  | Occurrence |  |  |  | Severity | [6 empty] | RPN
Number | Phase | Risk | Cause | Occurrence | Safety | Cost | Time | Scope | Quality | Environment | Regulation | Safety-RPN | Cost-RPN | Time-RPN | Scope-RPN | Quality-RPN | Env-RPN | Reg-RPN
1 | Deployment/Recovery | Install unsuccessful | Damage to flood ports during staging, transport etc. | 2 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0
2 | Operation | Low AEP | Time to recover float to surface reduces production of energy | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0
3 | Operation | No AEP | Failure of flood port valves cause float to sink | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 4 | 6 | 4 | 4 | 4 | 0 | 0
4 | Operation | Environmental | Noise associated with compressors disturb marine environment | 2 | 0 | 2 | 3 | 3 | 2 | 0 | 3 | 0 | 4 | 6 | 6 | 4 | 0 | 6
5 | Operation | Low AEP | Detuning of device due to float mass balance (design risk) | 2 | 0 | 2 | 3 | 2 | 2 | 0 | 0 | 0 | 4 | 6 | 4 | 4 | 0 | 0
6 | Operation | O&M costs | Additional component upkeep reliability | 2 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 6 | 6 | 6 | 6 | 4 | 0 | 0
7 | Operation | Low AEP | Mooring float interactions, loads during energetic seas (design risk) | 4 | 3 | 3 | 3 | 3 | 3 | 0 | 1 | 12 | 12 | 12 | 12 | 12 | 0 | 4
8 | Operation | Low AEP | Inability to tune performance via ballasting | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0
9 | Survival | Safety | Marine personnel risks monitoring sinking | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 0 | 6 | 9 | 6 | 6 | 6 | 6 | 0
10 | Survival | Heave plate failure | Large wave causes heave plate collision with sea floor | 1 | 3 | 3 | 2 | 3 | 3 | 0 | 2 | 3 | 3 | 2 | 3 | 3 | 0 | 2
11 | Survival | Heave plate failure | Vortex shedding large amplitude oscillations of heave plate | 1 | 2 | 3 | 2 | 3 | 2 | 0 | 0 | 2 | 3 | 2 | 3 | 2 | 0 | 0
12 | Survival | No AEP | Umbilical tangled, fouled during sinking/recovery (design risk) | 1 | 3 | 4 | 3 | 3 | 3 | 2 | 2 | 3 | 4 | 3 | 3 | 3 | 2 | 2
13 | Survival | Low AEP | Failure of compressor, inability to recover float | 1 | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 4 | 5 | 3 | 4 | 3 | 3 | 2
14 | Survival | Low AEP | Insufficient air source for compressor, inability to recover float | 2 | 4 | 5 | 3 | 3 | 2 | 3 | 0 | 8 | 10 | 6 | 6 | 4 | 6 | 0
15 | Survival | Low AEP | Leaks in air supply, inability to recover float | 2 | 4 | 5 | 3 | 3 | 2 | 3 | 0 | 8 | 10 | 6 | 6 | 4 | 6 | 0
16 | Survival | Low AEP | Additional sediment collection in heave plate at increased depths | 2 | 3 | 4 | 3 | 3 | 2 | 2 | 0 | 6 | 8 | 6 | 6 | 4 | 4 | 0
17 | Survival | Low AEP | Loss of communications in sunken state, inability to recover | 2 | 4 | 5 | 3 | 3 | 2 | 3 | 0 | 8 | 10 | 6 | 6 | 4 | 6 | 0
18 | Survival | Tether failure | Loss of communications, surface float not sunk in extreme seas | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 6 | 6 | 6
19 | Survival | Tether failure | Float not sunk in time to avoid extreme seas | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 6 | 6 | 6
20 | Survival | Tether failure | Float surfaces before extreme seas fully subsided | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 6 | 6 | 6
21 | Survival | Tether failure | Flood ports fail due to biologically-driven corrosion | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3
22 | Survival | Tether failure | Flood port failure, remain closed, surface float not sunk | 2 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 6 | 6 | 6 | 6 | 6
23 | Survival | Tether failure | Float not sunk reduced ballast volume due to biological growth | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3
24 | Survival | Tether failure | Large wave interacts with float, submerged depth insufficient | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 0
25 | Survival | Tether failure | Trim stability while sinking (design risk) | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 0
26 | Survival | Tether failure | Float becomes sensitive environmental habitat, inability to sink | 2 | 1 | 2 | 3 | 3 | 3 | 0 | 3 | 2 | 4 | 6 | 6 | 6 | 0 | 6
27 | Survival | Mooring failure | Current induced forces increase mooring loads in sunken state | 3 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 3 | 0 | 0
28 | Survival | Mooring failure | Wave interactions overload mooring line in sunken state | 1 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 4 | 4 | 3 | 3 | 3 | 2 | 2
29 | Survival | Mooring failure | Mooring line cut due to vessel running over, low visibility when sunk | 1 | 4 | 3 | 3 | 3 | 1 | 1 | 2 | 4 | 3 | 3 | 3 | 1 | 1 | 2
30 | Survival | Mooring failure | Mooring interconnects fail due to increased range of motion | 1 | 4 | 3 | 3 | 2 | 1 | 1 | 2 | 4 | 3 | 3 | 2 | 1 | 1 | 2
31 | Survival | Mooring failure | Entanglement with vessel while sinking | 1 | 5 | 4 | 1 | 2 | 1 | 4 | 3 | 5 | 4 | 1 | 2 | 1 | 4 | 3
32 | Survival | Mooring failure | Entanglement with vessel while surfacing | 1 | 5 | 4 | 1 | 2 | 1 | 4 | 3 | 5 | 4 | 1 | 2 | 1 | 4 | 3
33 | Survival | Mooring failure | Entanglement with marine animal while sinking | 1 | 3 | 2 | 1 | 2 | 0 | 1 | 4 | 3 | 2 | 1 | 2 | 0 | 1 | 4
34 | Survival | Mooring failure | Entanglement with marine animal while surfacing | 1 | 3 | 2 | 1 | 2 | 0 | 1 | 4 | 3 | 2 | 1 | 2 | 0 | 1 | 4
35 | Survival | Hull structure failure | Flood ports plugged, ballast tanks fail due to pressure when blown | 1 | 3 | 4 | 3 | 1 | 0 | 2 | 2 | 3 | 4 | 3 | 1 | 0 | 2 | 2
36 | Survival | Hull structure failure | Exhaust port plugged, ballast tanks fail due to pressure when sunk | 1 | 3 | 4 | 3 | 1 | 0 | 2 | 2 | 3 | 4 | 3 | 1 | 0 | 2 | 2
37 | Survival | Hull structure failure | Collision with vessel while surfacing | 1 | 5 | 4 | 2 | 1 | 0 | 4 | 3 | 5 | 4 | 2 | 1 | 0 | 4 | 3
38 | Survival | Hull structure failure | Collision with debris while surfacing | 1 | 4 | 3 | 2 | 1 | 0 | 3 | 2 | 4 | 3 | 2 | 1 | 0 | 3 | 2
39 | Survival | Hull structure failure | Vessel collision with float due to reduced visibility while sunk | 2 | 3 | 2 | 2 | 1 | 0 | 4 | 3 | 6 | 4 | 4 | 2 | 0 | 8 | 6
40 | Survival | System loss | Bulkhead seal failure chemically-driven corrosion (design risk) | 1 | 4 | 3 | 2 | 1 | 0 | 3 | 2 | 4 | 3 | 2 | 1 | 0 | 3 | 2
41 | Survival | System loss | Bulkhead seal failure fatigue (design risk) | 1 | 4 | 3 | 2 | 1 | 0 | 3 | 2 | 4 | 3 | 2 | 1 | 0 | 3 | 2
42 | Survival | System loss | Flooding thru LTU ports at depth (design risk) | 2 | 4 | 3 | 2 | 2 | 2 | 3 | 2 | 8 | 6 | 4 | 4 | 4 | 6 | 4
43 | Survival | System loss | Hydrostatic pressure loads, hull penetration seal failure (design risk) | 1 | 4 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 4 | 3 | 3 | 2 | 4 | 2
44 | Survival | Safety | Increased risk to personnel for repairing float while sunk | 1 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 2 | 2 | 2 | 2
45 | Survival | Safety | Endangerment of vessels illegally tied to float while sinking | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 4 | 1
46 | Survival | Environmental | Collision with marine animal while surfacing | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Survival | Environmental | Collision with marine animal while sinking | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 6
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Set down of heave plate on seafloor additional risks (only suitable sites considered) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Operation | Heave plate failure | Large wave causes heave plate collision with sea floor | 1 | 3 | 4 | 3 | 2 | 2 | 3 | 3 | 3 | 4 | 3 | 2 | 2 | 3 | 3
49 | Operation | Low AEP | Additional sediment collection in heave plate at increased depth | 1 | 3 | 3 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 0 | 2 | 2 | 0 | 0
50 | Operation | O&M costs | Additional tether length required, upkeep and reliability | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 6 | 6 | 4 | 4 | 4 | 4 | 0
51 | Survival | Environmental | Scouring damage to seafloor due to heave plate motions | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 2
52 | Survival | Environmental | Collision with marine animal while setting heave plate down | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Survival | Environmental | Heave plate becomes environmental habitat on sea floor | 5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0
54 | Survival | Low AEP | Suction pressure on heave plate, inability to recover | 2 | 4 | 3 | 2 | 2 | 1 | 2 | 2 | 8 | 6 | 4 | 4 | 2 | 4 | 4
55 | Survival | Low AEP | Heave plate becomes fully buried, sediment fills structure | 1 | 4 | 4 | 2 | 2 | 1 | 3 | 2 | 4 | 4 | 2 | 2 | 1 | 3 | 2
56 | Survival | Low AEP | Sediment collection in heave plate while at sea floor | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 0
57 | Survival | Heave plate failure | Structural damage to heave plate during set down | 1 | 3 | 4 | 3 | 2 | 2 | 2 | 0 | 3 | 4 | 3 | 2 | 2 | 2 | 0
58 | Survival | Heave plate failure | Structural damage due to heave plate surge/sway/yaw on sea floor | 1 | 3 | 4 | 3 | 2 | 2 | 2 | 0 | 3 | 4 | 3 | 2 | 2 | 2 | 0
59 | Survival | Heave plate failure | Large wave causes heave plate to lift and fall damaging structure | 1 | 3 | 4 | 3 | 2 | 2 | 4 | 0 | 3 | 4 | 3 | 2 | 2 | 4 | 0
60 | Survival | Low AEP | Increased biological growth on heave plate at sea floor | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0
61 | Survival | Low AEP | Set down procedure increases time to enter survival state | 2 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Valid data fields
Important Note: use the following procedure to add/or change valid data fields for this risk register
1) add new data option below appropriate column within "Valid data field" worksheet
2) click (Ctrl+F3), for Name Manager window
3) highlight Name being modified, click "Edit" icon
4) under "Refers to:", extend range to include new data
5) click "OK" icon
6) click "Close" icon
7) new data should now appear as option within "Risk Register" worksheet
RBS | Technical | Management | Commercial | External | TRL | TPL | Life | Owner | + or - | Type | Severity | Frequency | NegResponse | PosResponse | Timing
Technical | 1.1 Scope definition | 2.1 Project management | 3.1 Contractual terms and conditions | 4.1 Legislation | NA | NA | NA | John Smith (COO) | - | S | 0 | 0 | avoid | exploit | now
Management | 1.2 Requirements definition | 2.2 Program/Portfolio management | 3.2 Internal procurement | 4.2 Exchange rates | All | All | Multiple (or all) life phases | Joe Doe (engineer) | + | C | 1 | 1 | transfer | share | before specification
Commercial | 1.3 Estimates, assumptions, constraints | 2.3 Operations management | 3.3 Suppliers and vendors | 4.3 Site/facilities | 1 | 1 | Specification | Barb Johnson (CFO) |  | T | 2 | 2 | mitigate | enhance | before design finalized
External | 1.4 Technical processes | 2.4 Organization | 3.4 Subcontracts | 4.4 Environmental/weather | 2 | 2 | Design | Diane Briggs (CEO) |  | P | 3 | 3 | accept | accept | before PO issued
| 1.5 Technology | 2.5 Human resourcing | 3.5 Client/customer stability | 4.5 Competition | 3 | 3 | Manufacturing |  |  | Q | 4 | 4 |  |  | before manufacturing
| 1.6 Technical interfaces | 2.6 Funding | 3.6 Partnerships and joint ventures | 4.6 Regulatory | 4 | 4 | Transportation |  |  | E | 5 | 5 |  |  | before assembly and commissioning
| 1.7 System reliability | 2.7 Communication | 3.7 LCOE | 4.7 Political | 5 | 5 | Assembly and commissioning |  |  | R |  |  |  |  | before decommissioning
| 1.8 Performance | 2.8 Information |  | 4.8 Force majeure | 6 | 6 | Normal power production | [7 empty] | January
| 1.9 Safety | 2.9 Quality |  | 4.9 External stakeholder | 7 | 7 | Extreme events | [7 empty] | February
| 1.10 Security | 2.10 Reputation |  |  | 8 | 8 | Faults | [7 empty] | March
[5 empty] | 9 | 9 | Maintenance | [7 empty] | April
[7 empty] | Repair | [7 empty] | May
[7 empty] | Decommissioning | [7 empty] | June
July
August
September
October
November
December