## Data Rights Notice
PROTECTED RIGHTS NOTICE
Use, reproduction, or disclosure is subject to the restrictions in Award No. DE-EE0008627 with the U.S. Department of Energy until July 19, 2024. Business Sensitive Information.

## 0100 Hull System
[13 empty] | Risk Ranking | [11 empty] | Updated Risk Ranking | [11 empty] | 2nd Updated Risk Ranking
0100 Hull Structure FMECA Table | [13 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Recommended Actions | Responsible Party | Actions Taken | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | 2nd Recommended Actions | Responsible Party (2nd) | Actions Taken (2nd) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Status (open or closed) | Notes
0100-1 | Hull | Wave activated body Provision of watertight compartment Structural connectivity & load transfer | 2 | Loading in wave environment, with large motions | Severe structural failure | Severe structural failure WEC is no longer functioning | Extreme wave event loading (Overloading) | Normal | none | none | 1) Surveillance (cameras, visual inspections) 2) SCADA (PTO sensors, water sensors, etc.) | Recovery and repair | 4 | 1 | 3 | 9 | 9 | Low | Low | Med | Med
0100-2 | Hull | Wave activated body Provision of watertight compartment Structural connectivity & load transfer | 2 | Loading in wave environment, with large motions | Severe structural failure | Severe structural failure WEC is no longer functioning | Fatigue | Normal | 1) FEA and fatigue analysis 2) High partial safety factor | 1) Strain sensors 2) Visual inspections where possible | 1) Surveillance (cameras, visual inspections) 2) SCADA (PTO sensors, water sensors, etc.) | Recovery and repair | 4 | 1 | 3 | 9 | 9 | Low | Low | Med | Med
0100-2 | Hull | Wave activated body Provision of watertight compartment Structural connectivity & load transfer | 2 | Loading in wave environment, with large motions | Severe structural failure | Severe structural failure WEC is no longer functioning | Corrosion | Normal | 1) Corrosion resistant materials 2) Coatings | 1) Visual inspections | 1) Surveillance (cameras, visual inspections) 2) SCADA (PTO sensors, water sensors, etc.) | Recovery and repair | 6 | 1 | 3 | 9 | 9 | Low | Low | Med | Med
0111-1 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Crack/hole in float | 1) Sub-optimal performance 2) change in buoyancy | Leak in hull (e.g. manufacturing flaw, assembly) *not boat strike* | Normal | 1) All ballast water below waterline 2) Foam fill open voids | none | 1) visual inspection of draft line on floats 2) average angle of the floats seen by encoders | Recovery and repair, in-situ if possible | 4 | 1 | 1 | 7 | 7 | Low | Low | Low | Low
0111-2 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Crack/hole in float | 1) Sub-optimal performance 2) change in buoyancy | Leak in hull - fatigue crack due to uncertainties in loading | Normal | 1) FEA and fatigue analysis 2) High partial safety factor 3) All ballast water below waterline 4) Foam fill open voids | none | 1) visual inspection of draft line on floats 2) average angle of the floats seen by encoders | Recovery and repair, in-situ if possible | 4 | 1 | 1 | 7 | 7 | Low | Low | Low | Low
0111-3 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Crack/hole in float | 1) Loss of performance 2) Loss of known physical parameters (weight of each component) 3) change in buoyancy | Debris caught between float and another body, leading to wear that creates a hole that changes buoyancy | Normal | 1) All ballast water below waterline 2) Foam fill open voids | surveillance camera checks/visual inspection | 1) visual inspection of draft line on floats 2) average angle of the floats seen by encoders | Recovery and repair, in-situ if possible | 5 | 1 | 1 | 7 | 7 | Low | Low | Med | Med
0111-4 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Crack/hole in float | 1) Loss of performance 2) Loss of known physical parameters (weight of each component) 3) change in buoyancy | Non-service Boat Strike | Normal | 1) Lights, radar reflectors (i.e., visibility) 2) All ballast water below waterline 3) Foam fill open voids | none | 1) visual inspection of draft line on floats 2) average angle of the floats seen by encoders | Recovery and repair, in-situ if possible | 7 | 1 | 1 | 6 | 7 | Low | Low | Med | Med
0111-5 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Locked / reduced motion | 1) Float becomes locked or reduced motion w.r.t. nacelle | Debris caught between float and nacelle (or spar) | Normal | smooth edges to reduce debris being able to be caught | surveillance camera checks/visual inspection | 1) PTO not moving or reduced motion 2) Surveillance cameras | Remove debris In situ or recovery repair of hull if warranted | 7 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0111-7 | Float(s) | Wave activated body Provision of watertight compartment | 2 | Loading in wave environment, with large motions | float breaks off | 1) Wave loading of float is no longer transferred to rotor 2) Loss of power production 3) Loss of float assembly | One arm breaks off and causes higher stress on other arm so both break and float is free | Normal | none | 1) Surveillance 2) Visual Detection 3) Recovery before second arm breaks | 1) Average angle of the floats seen by encoders 2) Surveillance | 1) Recover float 2) Recover WEC and reatachment if possible | 4 | 1 | 2 | 8 | 8 | Low | Low | Med | Med
0136-1 | Nacelle Hull | Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Hole in single comparment | 1) water ingress through hole (bilge removes water from compartment) | Leak in hull (e.g. manufacturing flaw, assembly) | Normal | 1) vacuum test all water tight compartments 2) Single empty compartment filling does not sink WEC 3) V&V for manufacturing and assembly | none | 1) water detection | Repair in-situ | 4 | 1 | 1 | 7 | 7 | Low | Low | Low | Low
0136-2 | Nacelle Hull | Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Hole in single comparment | 1) water ingress through hole (bilge removes water from compartment) | Leak in hull - fatigue crack due to uncertainties in loading | Normal | 1) Single empty compartment filling does not sink WEC | none | 1) water detection | Recover and repair | 4 | 1 | 1 | 7 | 7 | Low | Low | Low | Low
0136-3 | Nacelle Hull | Provision of watertight compartment | 2 | Loading in wave environment, with large motions | Hole in single comparment | 1) water ingress through hole (bilge removes water from compartment) | Non-service boat strike | Normal | 1) lights, Radar reflectors (visibility) 2) Single empty compartment filling does not sink WEC | none | 1) water detection | In situ repair if possible (hole above waterline and known location) Worst case: recovery, inspection and repair of WEC. | 7 | 1 | 1 | 6 | 7 | Low | Low | Med | Med

## version history
Title | Low Power 8627 Hull Structure FMECA
Doc No | LP-8627-RR-0100
Version | 1
Authored | E Hammagren
Reviewed | E Amon
Approved Dist.
Approved Final
Version | Date | Summary
1 | 2019-06-13 | Initial draft based on system concept

## set up
| Risk = Occ + Sev | [11 empty] | Note:
| Severity | [11 empty] | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
10 | Low | Med | Med | Med | Med | High | High | High | High | High
9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11
8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15
7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High
6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High
5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med
4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med |  | Low | Tolerable, no engineer action required
3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med |  | Med | Undesirable, consider engineer actions to mitigate risk
2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med |  | High | Intolerable, engineering action required
1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low
Occurrence | [5 empty] | Severity
Rating | Occurrence |  | Annual Failure Rate | Return Period [years] |  | Rating | Severity | Human Safety |  | Environment |  | WEC Operation |  | Assets
1 | Exceptionally unlikely to occur |  | 1e-05 | 100000 |  | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) |  | Negligible pollution or no effect on environment |  | Negligible effect on performance |  | Negligible
2 |  |  | 3.1623e-05 | 31600 |  | 2 | [7 empty] | [1.5k USD]
3 | Extremely unlikely to occur |  | 0.0001 | 10000 |  | 3 | Minor | Minor injuries, health effects (e.g. stitches) |  | Minor pollution / slight effect on environment (min disruption on marine life) |  | Minor system degradation |  | Repairable in-situ, at next maintenance interval [3k USD]
4 |  |  | 0.00031623 | 3160 |  | 4 |  | Moderate injuries and/or health effects (e.g. broken bone) |  |  |  | Moderate system degradation (e.g. loss of function, repairable in-situ) |  | Repairable in-situ, outside maintenance interval (1 day) [5k USD]
5 | Very unlikely to occur |  | 0.001 | 1000 |  | 5 | Major |  |  | Limited levels of pollution, manageable / moderate effect on environment |  |  |  | Repairable in-situ, outside maintenance interval (1 week) [15k USD]
6 |  |  | 0.0031623 | 316 |  | 6 | [5 empty] | Major system degradation or loss of operation for 1 month |  | [25k USD]
7 | Rarely expected to occur |  | 0.01 | 100 |  | 7 | Critical | Hospitalization (with full recovery) |  | Moderate pollution (some clean-up costs) / Serious effect on environment |  | Major system degradation or loss of operation for 3 months |  | Dry dock required for repair [50k USD]
8 |  |  | 0.031623 | 31.6 |  | 8 | [5 empty] | Critical system degradation or loss of operation for 6 months |  | [150k USD]
9 | One or more during 20 yr lifetime |  | 0.1 | 10 |  | 9 | Catastrophic | Hospitalization (with lasting disabilities) |  | Major pollution (significant clean-up costs) / disastrous effects on the environment |  | Failure to generate power for remainder of project, complete failure |  | Loss of device [500k USD]
10 |  |  | 0.31623 | 3.16 |  | 10 |  | A fatality

## linkedPage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | Risk = Occ + Sev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note:
0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
0 | Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
0 | 10 | Low | Med | Med | Med | Med | High | High | High | High | High | 0 | 0 | 0 | 0 | 0
0 | 9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11 | 0 | 0 | 0
0 | 8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15 | 0 | 0 | 0
0 | 7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High | 0 | 0 | 0 | 0 | 0
0 | 6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High | 0 | 0 | 0 | 0 | 0
0 | 5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med | 0 | 0 | 0 | 0 | 0
0 | 4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med | 0 | Low | Tolerable, no engineer action required | 0 | 0
0 | 3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med | 0 | Med | Undesirable, consider engineer actions to mitigate risk | 0 | 0
0 | 2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med | 0 | High | Intolerable, engineering action required | 0 | 0
0 | 1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Occurrence | 0 | 0 | 0 | 0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Rating | Occurrence | 0 | Annual Failure Rate | Return Period [years] | 0 | Rating | Severity | Human Safety | 0 | Environment | 0 | WEC Operation | 0 | Assets | 0
0 | 1 | Exceptionally unlikely to occur | 0 | 1e-05 | 100000 | 0 | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) | 0 | Negligible pollution or no effect on environment | 0 | Negligible effect on performance | 0 | Negligible | 0
0 | 2 | 0 | 0 | 3.1623e-05 | 31600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [1.5k USD] | 0
0 | 3 | Extremely unlikely to occur | 0 | 0.0001 | 10000 | 0 | 3 | Minor | Minor injuries, health effects (e.g. stitches) | 0 | Minor pollution / slight effect on environment (min disruption on marine life) | 0 | Minor system degradation | 0 | Repairable in-situ, at next maintenance interval [3k USD] | 0
0 | 4 | 0 | 0 | 0.00031623 | 3160 | 0 | 4 | 0 | Moderate injuries and/or health effects (e.g. broken bone) | 0 | 0 | 0 | Moderate system degradation (e.g. loss of function, repairable in-situ) | 0 | Repairable in-situ, outside maintenance interval (1 day) [5k USD] | 0
0 | 5 | Very unlikely to occur | 0 | 0.001 | 1000 | 0 | 5 | Major | 0 | 0 | Limited levels of pollution, manageable / moderate effect on environment | 0 | 0 | 0 | Repairable in-situ, outside maintenance interval (1 week) [15k USD] | 0
0 | 6 | 0 | 0 | 0.0031623 | 316 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Major system degradation or loss of operation for 1 month | 0 | [25k USD] | 0
0 | 7 | Rarely expected to occur | 0 | 0.01 | 100 | 0 | 7 | Critical | Hospitalization (with full recovery) | 0 | Moderate pollution (some clean-up costs) / Serious effect on environment | 0 | Major system degradation or loss of operation for 3 months | 0 | Dry dock required for repair [50k USD] | 0
0 | 8 | 0 | 0 | 0.031623 | 31.6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | Critical system degradation or loss of operation for 6 months | 0 | [150k USD] | 0
0 | 9 | One or more during 20 yr lifetime | 0 | 0.1 | 10 | 0 | 9 | Catastrophic | Hospitalization (with lasting disabilities) | 0 | Major pollution (significant clean-up costs) / disastrous effects on the environment | 0 | Failure to generate power for remainder of project, complete failure | 0 | Loss of device [500k USD] | 0
0 | 10 | 0 | 0 | 0.31623 | 3.16 | 0 | 10 | 0 | A fatality | 0 | 0 | 0 | 0 | 0 | 0 | 0