## Data Rights Notice
PROTECTED RIGHTS NOTICE
Use, reproduction, or disclosure is subject to the restrictions in Award No. DE-EE0008627 with the U.S. Department of Energy until July 19, 2024. Business Sensitive Information.

## 0200 PTO System
[13 empty] | Risk Ranking | [11 empty] | Updated Risk Ranking | [11 empty] | 2nd Updated Risk Ranking
0100 Hull Structure FMECA Table | [13 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Recommended Actions | Responsible Party | Actions Taken | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | 2nd Recommended Actions | Responsible Party (2nd) | Actions Taken (2nd) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Status (open or closed) | Notes
210-1 | Generator | Electromechanical energy conversion | 2 | Marine application | Fire/smoke due to electrical short Loss of generator Loss of PTO | 1) Generator is electricaly isolated 2) PTO is shutdown and electrically isolated. 3) Heat production 4) smoke/fire 5) Fire spreads | Electrical short (non-moisture or corrosion) - Short in generator - Short in connector Creating an overheating condition which leads to fire/smoke | Normal | 1) OTS industry proven components 2) Circuit breaker isolates motor on over current and/or ground fault 3) Quality marine design and manufacturing 4) V&V (insulation check, pulse test, high voltage test) | SCADA - motor drive feedback and current sensing, PTO temperature, | 1) PTO shutdown fault Alarm 2) PTO fire Alarm 3) PTO compartment air quality monitoring & alarm 4) Circuit breaker status and/or overcurrent detection | recovery and repair | 4 | 1 | 2 | 9 | 9 | Low | Low | Med | Med
210-2 | Generator | Electromechanical energy conversion | 2 | Marine application | Loss of generating capabilities | 1) Generator shut down | Corrosion induced failure | Normal | 1) OTS industry proven components 2) corrosion resistant materials | 1) Visual inspections | 1) PTO shutdown fault Alarm | recovery and repair | 6 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
210-3 | Generator | Electromechanical energy conversion | 2 | Marine application | Loss of generating capabilities | 1) Generator shut down | Manufacturing defect results in failure | Normal | 1) Commercial product 2) V&V (QC) | 1) Visual inspection | 1) PTO shutdown fault Alarm | recovery and repair | 6 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
210-4 | Generator | Electromechanical energy conversion | 2 | Marine application | Loss of generating capabilities | 1) Generator shut down | Vibration induced failure | Normal | 1) Vibration monitoring 2) Structural design | 1) Vibration monitoring | 1) PTO shutdown fault Alarm | recovery and repair | 5 | 1 | 1 | 7 | 7 | Low | Low | Med | Med
250-1 | PTO shaft | Transmit torque from float drive arm to the rotor | 2 | Loading | Material fracture | 1) Shaft broken off 2) Loss of torque transmitted to PTO 3) Damage to hull from broken off shaft and float arm | Wear/fatigue | Normal | None | None | 1) Vibration and temperature sensors 2) Abnormal speed with respect to the wave climate and damping | recovery and repair | 5 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
250-2 | PTO shaft | Transmit torque from float drive arm to the rotor | 2 | Loading | Material fracture | 1) Shaft broken off 2) Loss of torque transmitted to PTO 3) Damage to hull from broken off shaft and float arm | Manufacturing defect | Normal | None | None | 1) Vibration and temperature sensors 2) Abnormal speed with respect to the wave climate and damping | recovery and repair | 4 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
250-3 | PTO shaft | Transmit torque from float drive arm to the rotor | 2 | Loading | Material fracture | 1) Shaft broken off 2) Loss of torque transmitted to PTO 3) Damage to hull from broken off shaft and float arm | Contamination, corrosion | Normal | None | None | 1) Vibration and temperature sensors 2) Abnormal speed with respect to the wave climate and damping | recovery and repair | 4 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
250-4 | PTO shaft | Transmit torque from float drive arm to the rotor | 2 | Loading | Material fracture | 1) Shaft broken off 2) Loss of torque transmitted to PTO 3) Damage to hull from broken off shaft and float arm | Extreme loading | Normal | None | None | 1) Vibration and temperature sensors 2) Abnormal speed with respect to the wave climate and damping | recovery and repair | 6 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
261-1 | Main Bearings | Allow smooth rotation of motor Constrain relative generator (and float/nacelle) motion to 1 DOF Transmit loads from drive arms to nacelle tube | 2 | Loading Maintenance intervals | Binding | 1) Damaged raceway 2) Broken rollers 3) Added friction | Wear/fatigue | Normal | None | none | 1) Vibration and temperature sensors 2) Abnormal speed with respect to the wave climate and damping | Moderate increase in friction accepted | 5 | 1 | 1 | 7 | 7 | Low | Low | Med | Med
261-2 | Main Bearings | Allow smooth rotation of motor Constrain relative generator (and float/nacelle) motion to 1 DOF Transmit loads from drive arms to nacelle tube | 2 | Loading Maintenance intervals | Binding | 1) Damaged raceway 2) Broken rollers 3) Added friction | Manufacturing defect | Normal | V&V | none | 1) Vibration sensors and bearing temperature 2) Abnormal speed with respect to the wave climate and damping | Moderate increase in friction accepted | 4 | 1 | 1 | 7 | 7 | Low | Low | Low | Low
261-3 | Main Bearings | Allow smooth rotation of motor Constrain relative generator (and float/nacelle) motion to 1 DOF Transmit loads from drive arms to nacelle tube | 2 | Loading Maintenance intervals | Binding | 1) Damaged raceway 2) Broken rollers 3) Added friction | Contamination, corrosion | Normal | Bearing seals, corrosion resistant materials | 1) Bearing and lubrication checks, look for signs of bearing failure and contaminants in used grease. | 1) Vibration sensors and bearing temperature 2) Abnormal speed with respect to the wave climate and damping | Moderate increase in friction accepted | 4 | 1 | 1 | 6 | 6 | Low | Low | Low | Low
261-4 | Main Bearings | Allow smooth rotation of motor Constrain relative generator (and float/nacelle) motion to 1 DOF Transmit loads from drive arms to nacelle tube | 2 | Loading Maintenance intervals | Binding | 1) Damaged raceway 2) Broken rollers 3) Added friction | Extreme loading | Normal | None | none | 1) Vibration sensors and bearing temperature 2) Abnormal speed with respect to the wave climate and damping | Moderate increase in friction accepted | 6 | 1 | 1 | 6 | 6 | Low | Low | Med | Med
261-5 | Main Bearings | Allow smooth rotation of motor Constrain relative generator (and float/nacelle) motion to 1 DOF Transmit loads from drive arms to nacelle tube | 2 | Loading Maintenance intervals | Bearing Failure | 1) Damaged raceway 2) Broken rollers 3) Added friction 4) Bearing damaged and unusable | Extreme loading | Normal | None | none | 1) Vibration sensors and bearing temperature 2) Abnormal speed with respect to the wave climate and damping | recovery and replacement | 5 | 1 | 1 | 7 | 7 | Low | Low | Med | Med
280-1 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Moderate Leak | 1) Completely flooded nacelle 2) Damage to PTO components | Wear/fatigue | Normal | None | none | 1) Water sensors | recovery and repair | 6 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-2 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Moderate Leak | 1) Completely flooded nacelle 2) Damage to PTO components | Manufacturing defect | Normal | None | none | 1) Water sensors | recovery and repair | 5 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-3 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Moderate Leak | 1) Completely flooded nacelle 2) Damage to PTO components | Contamination puncture | Normal | None | none | 1) Water sensors | recovery and repair | 6 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-4 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Moderate Leak | 1) Completely flooded nacelle 2) Damage to PTO components | Deformation of shaft | Normal | None | none | 1) Water sensors | recovery and repair | 4 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-5 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Large leak | 1) Completely flooded nacelle 2) Damage to PTO components | Wear/fatigue | Normal | None | none | 1) Water sensors | recovery and repair | 5 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-6 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Large leak | 1) Completely flooded nacelle 2) Damage to PTO components | Manufacturing defect | Normal | None | none | 1) Water sensors | recovery and repair | 4 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-7 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Large leak | 1) Completely flooded nacelle 2) Damage to PTO components | Contamination puncture | Normal | None | none | 1) Water sensors | recovery and repair | 5 | 1 | 1 | 8 | 8 | Low | Low | Med | Med
280-8 | Shaft Seals | Maintain watertight integrity of Hull structure around the PTO shaft | 2 | Loading Maintenance intervals Long term behavior | Large leak | 1) Completely flooded nacelle 2) Damage to PTO components | Deformation of shaft | Normal | None | none | 1) Water sensors | recovery and repair | 3 | 1 | 1 | 8 | 8 | Low | Low | Low | Low

## version history
Title | Low Power 8627 PTO Structure FMECA
Doc No | LP-8627-RR-0200
Version | 1
Authored | E Hammagren
Reviewed | E Amon
Approved Dist.
Approved Final
Version | Date | Summary
1 | 2019-06-13 | Initial draft based on system concept

## set up
| Risk = Occ + Sev | [11 empty] | Note:
| Severity | [11 empty] | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
10 | Low | Med | Med | Med | Med | High | High | High | High | High
9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11
8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15
7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High
6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High
5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med
4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med |  | Low | Tolerable, no engineer action required
3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med |  | Med | Undesirable, consider engineer actions to mitigate risk
2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med |  | High | Intolerable, engineering action required
1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low
Occurrence | [5 empty] | Severity
Rating | Occurrence |  | Annual Failure Rate | Return Period [years] |  | Rating | Severity | Human Safety |  | Environment |  | WEC Operation |  | Assets
1 | Exceptionally unlikely to occur |  | 1e-05 | 100000 |  | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) |  | Negligible pollution or no effect on environment |  | Negligible effect on performance |  | Negligible
2 |  |  | 3.1623e-05 | 31600 |  | 2 | [7 empty] | [1.5k USD]
3 | Extremely unlikely to occur |  | 0.0001 | 10000 |  | 3 | Minor | Minor injuries, health effects (e.g. stitches) |  | Minor pollution / slight effect on environment (min disruption on marine life) |  | Minor system degradation |  | Repairable in-situ, at next maintenance interval [3k USD]
4 |  |  | 0.00031623 | 3160 |  | 4 |  | Moderate injuries and/or health effects (e.g. broken bone) |  |  |  | Moderate system degradation (e.g. loss of function, repairable in-situ) |  | Repairable in-situ, outside maintenance interval (1 day) [5k USD]
5 | Very unlikely to occur |  | 0.001 | 1000 |  | 5 | Major |  |  | Limited levels of pollution, manageable / moderate effect on environment |  |  |  | Repairable in-situ, outside maintenance interval (1 week) [15k USD]
6 |  |  | 0.0031623 | 316 |  | 6 | [5 empty] | Major system degradation or loss of operation for 1 month |  | [25k USD]
7 | Rarely expected to occur |  | 0.01 | 100 |  | 7 | Critical | Hospitalization (with full recovery) |  | Moderate pollution (some clean-up costs) / Serious effect on environment |  | Major system degradation or loss of operation for 3 months |  | Dry dock required for repair [50k USD]
8 |  |  | 0.031623 | 31.6 |  | 8 | [5 empty] | Critical system degradation or loss of operation for 6 months |  | [150k USD]
9 | One or more during 20 yr lifetime |  | 0.1 | 10 |  | 9 | Catastrophic | Hospitalization (with lasting disabilities) |  | Major pollution (significant clean-up costs) / disastrous effects on the environment |  | Failure to generate power for remainder of project, complete failure |  | Loss of device [500k USD]
10 |  |  | 0.31623 | 3.16 |  | 10 |  | A fatality

## linkedPage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | Risk = Occ + Sev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note:
0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
0 | Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
0 | 10 | Low | Med | Med | Med | Med | High | High | High | High | High | 0 | 0 | 0 | 0 | 0
0 | 9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11 | 0 | 0 | 0
0 | 8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15 | 0 | 0 | 0
0 | 7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High | 0 | 0 | 0 | 0 | 0
0 | 6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High | 0 | 0 | 0 | 0 | 0
0 | 5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med | 0 | 0 | 0 | 0 | 0
0 | 4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med | 0 | Low | Tolerable, no engineer action required | 0 | 0
0 | 3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med | 0 | Med | Undesirable, consider engineer actions to mitigate risk | 0 | 0
0 | 2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med | 0 | High | Intolerable, engineering action required | 0 | 0
0 | 1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Occurrence | 0 | 0 | 0 | 0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Rating | Occurrence | 0 | Annual Failure Rate | Return Period [years] | 0 | Rating | Severity | Human Safety | 0 | Environment | 0 | WEC Operation | 0 | Assets | 0
0 | 1 | Exceptionally unlikely to occur | 0 | 1e-05 | 100000 | 0 | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) | 0 | Negligible pollution or no effect on environment | 0 | Negligible effect on performance | 0 | Negligible | 0
0 | 2 | 0 | 0 | 3.1623e-05 | 31600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [1.5k USD] | 0
0 | 3 | Extremely unlikely to occur | 0 | 0.0001 | 10000 | 0 | 3 | Minor | Minor injuries, health effects (e.g. stitches) | 0 | Minor pollution / slight effect on environment (min disruption on marine life) | 0 | Minor system degradation | 0 | Repairable in-situ, at next maintenance interval [3k USD] | 0
0 | 4 | 0 | 0 | 0.00031623 | 3160 | 0 | 4 | 0 | Moderate injuries and/or health effects (e.g. broken bone) | 0 | 0 | 0 | Moderate system degradation (e.g. loss of function, repairable in-situ) | 0 | Repairable in-situ, outside maintenance interval (1 day) [5k USD] | 0
0 | 5 | Very unlikely to occur | 0 | 0.001 | 1000 | 0 | 5 | Major | 0 | 0 | Limited levels of pollution, manageable / moderate effect on environment | 0 | 0 | 0 | Repairable in-situ, outside maintenance interval (1 week) [15k USD] | 0
0 | 6 | 0 | 0 | 0.0031623 | 316 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Major system degradation or loss of operation for 1 month | 0 | [25k USD] | 0
0 | 7 | Rarely expected to occur | 0 | 0.01 | 100 | 0 | 7 | Critical | Hospitalization (with full recovery) | 0 | Moderate pollution (some clean-up costs) / Serious effect on environment | 0 | Major system degradation or loss of operation for 3 months | 0 | Dry dock required for repair [50k USD] | 0
0 | 8 | 0 | 0 | 0.031623 | 31.6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | Critical system degradation or loss of operation for 6 months | 0 | [150k USD] | 0
0 | 9 | One or more during 20 yr lifetime | 0 | 0.1 | 10 | 0 | 9 | Catastrophic | Hospitalization (with lasting disabilities) | 0 | Major pollution (significant clean-up costs) / disastrous effects on the environment | 0 | Failure to generate power for remainder of project, complete failure | 0 | Loss of device [500k USD] | 0
0 | 10 | 0 | 0 | 0.31623 | 3.16 | 0 | 10 | 0 | A fatality | 0 | 0 | 0 | 0 | 0 | 0 | 0