## Data Rights Notice
PROTECTED RIGHTS NOTICE
Use, reproduction, or disclosure is subject to the restrictions in Award No. DE-EE0008627 with the U.S. Department of Energy until July 19, 2024. Business Sensitive Information.

## 0400 System
[13 empty] | Risk Ranking | [11 empty] | Updated Risk Ranking | [11 empty] | 2nd Updated Risk Ranking
0400 SCADA FMECA Table | [13 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class | [7 empty] | Severity Class |  |  |  | Risk Class
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Recommended Actions | Responsible Party | Actions Taken | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | 2nd Recommended Actions | Responsible Party (2nd) | Actions Taken (2nd) | Occurrence | Human Safety | Environment | Operation | Assets | Human Safety | Environment | Operation | Assets | Status (open or closed) | Notes
0400-1 | SCADA Components | Control and data collection | 2 | Marine application Vibration levels | Power loss | Power loss due to short or open circuit, Damage to SCADA system | Electrical short/open, Internal component failure, wiring/installation issue, corrosion, vibration and or motion fatigue | Normal | Airtight enclosures, Low Power, V&V (QA/QC), vibration damping mounts | V&V(QA/QC of components and build), vibration measurement, water intrusion sensor | Emergency system fire alarm, Enclosure temperature, surveilance camera, visual inspection | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0400-2 | SCADA Components | Control and data collection | 2 | Marine application Vibration levels | Communications failure | Loss of communications between components interrupts data feed | Electrical short/open, Internal component failure, wiring/installation issue, corrosion, vibration and or motion fatigue | Normal | Airtight enclosures, Low Power, V&V (QA/QC), vibration damping mounts | V&V(QA/QC of components and build), vibration measurement, water intrusion sensor | Emergency system fire alarm, Enclosure temperature, surveilance camera, visual inspection | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0400-3 | SCADA Components | Control and data collection | 2 | Marine application Vibration levels | Hardware fault | Component failure/error leads to system malfunction | Electrical short/open, Internal component failure, manufacturing error, corrosion, vibration and or motion fatigue | Normal | Airtight enclosures, Low Power, V&V (QA/QC), vibration damping mounts | V&V(QA/QC of components and build), vibration measurement, water intrusion sensor | Emergency system fire alarm, Enclosure temperature, surveilance camera, visual inspection | In-situ repair or replacement of comonents effected | 7 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0400-4 | SCADA components | Control and data collection | 2 | Marine application Vibration levels | Fire/smoke | 1) Power loss due to short or open circuit 2) Damage to SCADA system | Electrical short/open, Internal component failure | Normal | Airtight enclosures, Low Power, V&V (QA/QC), vibration damping mounts | 1) Fire/smoke alarm | 1) Nacelle fire alarm 2) Nacelle temperature 3) Surveilance camera 4) visual inspection | In-situ repair or replacement of comonents effected | 7 | 1 | 3 | 5 | 5 | Low | Low | Med | Med
0410-1 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Wiring Issue - unknown internal fault - unknown poor solder joint - wire chaffe due to improper routing | Normal | 1) V&V 2) Redundant encoders | 1) None | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 7 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-2 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Corrosion induced failure | Normal | 1) Material selection 2) IP 67 3) sealed clean environment 4) Redundant encoders | 1) water intrusion sensor | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 6 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-3 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Contamination induced failure | Normal | 1) Thorough cleaning at commissioning 2) Redundant encoders 3) sealed clean environment | 1) None | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 7 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-4 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Improper installation or manufacturing defect results in failure | Normal | 1) V&V 2) Redundant encoders | 1) None | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 7 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-5 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Software / programming error during program revision. | Normal | 1) V&V 2) Security | 1) None | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Manual correction of software/programming error, onboard or remotely. | 5 | 1 | 1 | 6 | 4 | Low | Low | Low | Low
0410-6 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Vibration and/or motion induced failure | Normal | 1) Modal analysis 2) Redundant encoders | 1) None | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 7 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-7 | PTO Position Encoder | Provide position feedback to drives | 2 | Marine application Vibration levels | Signal failure | 1) Single encoder fail 2) Loss of position feedback | Water induced failure (non-corrosion) | Normal | 1) IP 67 2) Redundant encoders | 1) water intrusion sensor | Encoder fault codes or erratic position feedback | Manual switch of encoders onboard Programmatically selected encoders from internal system comparison. | 7 | 1 | 1 | 2 | 4 | Low | Low | Low | Low
0410-8 | PTO Position Encoder | Provide position feedback to motor drive | 2 | Marine application Vibration levels | Power loss | Loss of generator control | Wiring / Installation issue, Corrosion, vibration fatigue | Normal | Marine rated Components, Sealed clean internal environment | V&V(QA/QC of components and build), vibration sensor | Encoder fault code | In-situ repair or replacement of comonents effected | 7 | 1 | 1 | 5 | 4 | Low | Low | Med | Low
0410-9 | Nacelle temperature | provides temperature of nacelle space | 2 | Marine application Vibration levels | Signal failure | loss of nacelle temp | Hardware or wiring failure | Normal | 1) Redundancy | 1) None | loss or saturation of temperature feedback | Manual in-situ repair and inspection | 8 | 1 | 1 | 2 | 1 | Low | Low | Low | Low
0410-10 | Nacelle humidity | provides humidity of nacelle space | 2 | Marine application Vibration levels | Signal failure | loss of nacelle humidity | Hardware or wiring failure | Normal | 1) Redundancy | 1) None | loss or saturation of nacelle humidity signal | Manual in-situ repair and inspection | 9 | 1 | 1 | 2 | 1 | Low | Low | Low | Low
0410-11 | Station power draw | Provides power usage stats for onboard components | 2 | Marine application Vibration levels | Signal failure | 1) No station power draw data | Hardware or wiring failure | Normal | none | 1) None | 1) Station power data lost | Manual in-situ repair and inspection | 8 | 1 | 1 | 2 | 2 | Low | Low | Low | Low
0410-12 | Water intrusion sensor | Monitors lower nacelle space for presence of water | 1 | none | Signal failure | inability to monitor for water intrusion, increases other components risk | Hardware or wiring failure | Normal | 1) Redundancy | 1) None | none, unless reduntant sensors are present | Manual in-situ repair and inspection | 8 | 1 | 1 | 3 | 1 | Low | Low | Low | Low
0410-13 | Cooling temp, pressure, flow sensor | Provides cooling data | 1 | none | Signal failure | 1) No cooling data from failed sensor | Hardware or wiring failure | Normal | 1) Redundancy | 1) None | 1) Cooling parameter data lost | Manual in-situ repair and inspection | 8 | 1 | 1 | 3 | 2 | Low | Low | Low | Low
0410-14 | Inertial measurement unit (IMU) | Provides nacelle body motion data | 1 | none | Signal failure | 1) No motion data from failed sensor | Hardware or wiring failure | Normal | 1) Redundancy, critical for model validation | 1) None | 1) IMU data lost | Manual in-situ repair and inspection | 8 | 1 | 1 | 3 | 3 | Low | Low | Low | Low
0410-15 | GPS & heading sensor | Provide GPS position and heading | 1 | none | Signal failure | 1) No GPS position or heading data from failed sensor | Hardware or wiring failure | Normal | none | 1) None | 1) GPS & heading data lost | Manual in-situ repair and inspection | 8 | 1 | 1 | 2 | 2 | Low | Low | Low | Low
0410-16 | Mooring load cell | Provide mooring load data | 1 | none | Signal failure | 1) No mooring tension from failed sensor | Hardware or wiring failure | Normal | 1) Redundancy 2) Mechanical safety bypass of load cell | 1) Inspection | 1) Mooring data lost | Manual in-situ repair and inspection | 9 | 1 | 1 | 2 | 4 | Low | Low | Low | Med
0410-17 | Vibration accelerometer | Provide vibration data | 1 | none | Signal failure | 1) No vibration data from failed sensor | Hardware or wiring failure | Normal | 1) Redundancy | 1) None | 1) Data lost | Manual in-situ repair and inspection on most locations | 8 | 1 | 1 | 3 | 3 | Low | Low | Low | Low
0430-1 | SCADA Control Server/PLC | Central Control computer and local data storage system | 2 | Marine application Vibration levels | PC Failure | Computer Component damaged, computer speed greatly reduced, faulty data capture, failure to properly record or report data and complete loss of control of Buoy | Corrosion induced Failure | Normal | Marine rated Components, Airtight enclosures, subsystem seperation | V&V(QA/QC of components and build), regular computer self diagnostics routine | Loss of Data flow to or from the Buoy, Visual inspection of components. | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0430-2 | SCADA Control Server/PLC | Central Control computer and local data storage system | 2 | Marine application Vibration levels | PC Failure | Computer Component damaged, computer speed greatly reduced, faulty data capture, failure to properly record or report data and complete loss of control of Buoy | Improper Installation or Manufacturing defect | Normal | Marine rated Components, Airtight enclosures, subsystem seperation | V&V(QA/QC of components and build), regular computer self diagnostics routine | Loss of Data flow to or from the Buoy, Visual inspection of components. | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0430-3 | SCADA Control Server/PLC | Central Control computer and local data storage system | 2 | Marine application Vibration levels | PC Failure | Computer Component knocked loose or damaged, computer speed greatly reduced, faulty data capture, failure to properly record or report data and complete loss of control of Buoy | Vibration or Motion induced Failure | Normal | Marine rated Components, Airtight enclosures, isolation mounts | V&V(QA/QC of components and build), regular computer self diagnostics routine | Loss of Data flow to or from the Buoy, Visual inspection of components. | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0430-3 | SCADA Control Server/PLC | Central Control computer and local data storage system | 2 | Marine application Vibration levels | PC Failure | Computer damaged, failure to record or report data and complete loss of control of Buoy | Water innundation Induced failure | Normal | Marine rated Components, Airtight enclosures, subsystem seperation | V&V(QA/QC of components and build), regular computer self diagnostics routine | Loss of Data flow to or from the Buoy, alarm system triggered, Visual inspection of components. | In-situ repair or replacement of comonents effected | 8 | 1 | 1 | 5 | 5 | Low | Low | Med | Med
0440-1 | Human Machine Interface (HMI) | Provides operator interface with SCADA | 1 | none | HMI freezes or crashes | 1) HMI crash 2) Motor controller uses default damping 3) Deviation from control plan 4) Temporary loss of data feed | Coding error | Normal | 1) V&V (QC) | 1) None | 1) Loss of HMI access or control | 1) Remote programming repair 2) In-situ repair | 10 | 1 | 1 | 3 | 2 | Low | Low | Med | Med
0450-1 | Communications | Provide communication between the WEC systems and shore based operations | 1 | none | communications failure | Loss of single or all communication paths to WEC | wiring fault, communication hardware failure, network failure | Normal | 1) Use marine COTS products 2) V&V (QC) 3) Redundant communication paths | 1) None | Loss of single or all communication paths to WEC | 1) Remote programming repair 2) In-situ repair | 10 | 1 | 1 | 3 | 2 | Low | Low | Med | Med
0460-1 | Data Server | Store all operational and performance data | 1 | none | Internal Server failure | 1) Server crash 2) loss of HMI access 3) loss of data access | Internal hard drive or other hardware fault, software conflict | Normal | 1) RAID hard drive arrays 2) Redundant power supplies 3) Solid-state hard drives | server health monitoring system (or rely on 3rd Party to maintain) | 1) Server crash 2) loss of HMI access 3) loss of data access | 1) In-situ repair | 10 | 1 | 1 | 3 | 2 | Low | Low | Med | Med
0470-1 | Software | Provide Programming Enviornment for SCADA development |  | none | Software Crash | Temporary lock out from ability to modify control states, Possible loss of control, data collection or generation ability. | Software glitch, out of bounds input | Normal or Compromised Operations | Watchdog timer for full system restart, remote restart capability via IP | V&V(QA/QC of software components and build) | 1) Server crash 2) loss of HMI access 3) loss of data access | 1) Remote programming repair 2) In-situ repair | 10 | 1 | 1 | 3 | 2 | Low | Low | Med | Med
0480-1 | Alarms, Diagnostics, & Fault Recovery | Automated condition monitoring Issue alarms Initiate corrective actions | 1 | none | System doesn't respond to event correctly or allow diagnostics | 1) potential damage to critical systems 2) inability to diagnose subsystem errors remotely 3) loss of WEC operation until in-situ repair | Coding error, communications fault | Normal | 1) V&V (QC) | 1) None | 1) notification of secondary failures caused by undetected alarm 2) inability to diagnose remotely 3) loss of fault recovery ability | 1) Remote programming repair 2) In-situ repair | 10 | 1 | 1 | 4 | 3 | Low | Low | Med | Med
0490-1 | Enclosures | Provide applicable IEC IP rating | 1 | none | enclosures leak | Corrosion, mechanical failure, water loads | Cabinet doors improperly closed or vibrate open | Normal | all enclosures will have more than 1 latch mechanism | physical confirmation of closure and V&V(QA/QC of components and build) | 1) high cabinet temperature and/or humidity | In-situ repair or replacement of comonents effected | 9 | 1 | 1 | 3 | 3 | Low | Low | Med | Med
0495-1 | Cabling | Data and electrical connectivity Water resistant | 1 | none | wiring failure | 1) loss of connectivity 2) short circuit leading to tripping protective circuit breaker 3) high impedance leading to impropoer sensor readings | corrosion, chaffe, electrical fault | Normal | 1) V&V 2) cable connections adequate for environment 3) routing/protection to avoid chaffe 4) proper circuit protection and loading | Periodic inspection of connectors and cable runs where possible | 1) loss of connectivity 2) tripped circuit breakers 3) sensors out of range or data corrupted | In-situ repair or replacement of comonents effected | 9 | 1 | 1 | 4 | 3 | Low | Low | Med | Med

## version history
Title | Low Power 8627 SCADA FMECA
Doc No | LP-8627-RR-0400
Version | 1
Authored | L Rummel
Reviewed | E Amon
Approved Dist.
Approved Final
Version | Date | Summary
1 | 2019-06-13 | Initial draft based on system concept

## set up
| Risk = Occ + Sev | [11 empty] | Note:
| Severity | [11 empty] | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
10 | Low | Med | Med | Med | Med | High | High | High | High | High
9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11
8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15
7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High
6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High
5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med
4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med |  | Low | Tolerable, no engineer action required
3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med |  | Med | Undesirable, consider engineer actions to mitigate risk
2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med |  | High | Intolerable, engineering action required
1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low
Occurrence | [5 empty] | Severity
Rating | Occurrence |  | Annual Failure Rate | Return Period [years] |  | Rating | Severity | Human Safety |  | Environment |  | WEC Operation |  | Assets
1 | Exceptionally unlikely to occur |  | 1e-05 | 100000 |  | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) |  | Negligible pollution or no effect on environment |  | Negligible effect on performance |  | Negligible
2 |  |  | 3.1623e-05 | 31600 |  | 2 | [7 empty] | [1.5k USD]
3 | Extremely unlikely to occur |  | 0.0001 | 10000 |  | 3 | Minor | Minor injuries, health effects (e.g. stitches) |  | Minor pollution / slight effect on environment (min disruption on marine life) |  | Minor system degradation |  | Repairable in-situ, at next maintenance interval [3k USD]
4 |  |  | 0.00031623 | 3160 |  | 4 |  | Moderate injuries and/or health effects (e.g. broken bone) |  |  |  | Moderate system degradation (e.g. loss of function, repairable in-situ) |  | Repairable in-situ, outside maintenance interval (1 day) [5k USD]
5 | Very unlikely to occur |  | 0.001 | 1000 |  | 5 | Major |  |  | Limited levels of pollution, manageable / moderate effect on environment |  |  |  | Repairable in-situ, outside maintenance interval (1 week) [15k USD]
6 |  |  | 0.0031623 | 316 |  | 6 | [5 empty] | Major system degradation or loss of operation for 1 month |  | [25k USD]
7 | Rarely expected to occur |  | 0.01 | 100 |  | 7 | Critical | Hospitalization (with full recovery) |  | Moderate pollution (some clean-up costs) / Serious effect on environment |  | Major system degradation or loss of operation for 3 months |  | Dry dock required for repair [50k USD]
8 |  |  | 0.031623 | 31.6 |  | 8 | [5 empty] | Critical system degradation or loss of operation for 6 months |  | [150k USD]
9 | One or more during 20 yr lifetime |  | 0.1 | 10 |  | 9 | Catastrophic | Hospitalization (with lasting disabilities) |  | Major pollution (significant clean-up costs) / disastrous effects on the environment |  | Failure to generate power for remainder of project, complete failure |  | Loss of device [500k USD]
10 |  |  | 0.31623 | 3.16 |  | 10 |  | A fatality

## linkedPage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | Risk = Occ + Sev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note:
0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - 'set up' and 'linkedPage' are both linked to workbook 'FMECA Master v3.xlsx'
0 | Occ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | - changes to the tables, risk scores, etc must be made in 'FMECA Master v3.xlsx'
0 | 10 | Low | Med | Med | Med | Med | High | High | High | High | High | 0 | 0 | 0 | 0 | 0
0 | 9 | Low | Low | Med | Med | Med | Med | High | High | High | High | low <= | 11 | 0 | 0 | 0
0 | 8 | Low | Low | Low | Med | Med | Med | Med | High | High | High | high> | 15 | 0 | 0 | 0
0 | 7 | Low | Low | Low | Low | Med | Med | Med | Med | High | High | 0 | 0 | 0 | 0 | 0
0 | 6 | Low | Low | Low | Low | Low | Med | Med | Med | Med | High | 0 | 0 | 0 | 0 | 0
0 | 5 | Low | Low | Low | Low | Low | Low | Med | Med | Med | Med | 0 | 0 | 0 | 0 | 0
0 | 4 | Low | Low | Low | Low | Low | Low | Low | Med | Med | Med | 0 | Low | Tolerable, no engineer action required | 0 | 0
0 | 3 | Low | Low | Low | Low | Low | Low | Low | Low | Med | Med | 0 | Med | Undesirable, consider engineer actions to mitigate risk | 0 | 0
0 | 2 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Med | 0 | High | Intolerable, engineering action required | 0 | 0
0 | 1 | Low | Low | Low | Low | Low | Low | Low | Low | Low | Low | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Occurrence | 0 | 0 | 0 | 0 | 0 | Severity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Rating | Occurrence | 0 | Annual Failure Rate | Return Period [years] | 0 | Rating | Severity | Human Safety | 0 | Environment | 0 | WEC Operation | 0 | Assets | 0
0 | 1 | Exceptionally unlikely to occur | 0 | 1e-05 | 100000 | 0 | 1 | Insignificant | Negligible injury, effect on health (e.g. band aid) | 0 | Negligible pollution or no effect on environment | 0 | Negligible effect on performance | 0 | Negligible | 0
0 | 2 | 0 | 0 | 3.1623e-05 | 31600 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [1.5k USD] | 0
0 | 3 | Extremely unlikely to occur | 0 | 0.0001 | 10000 | 0 | 3 | Minor | Minor injuries, health effects (e.g. stitches) | 0 | Minor pollution / slight effect on environment (min disruption on marine life) | 0 | Minor system degradation | 0 | Repairable in-situ, at next maintenance interval [3k USD] | 0
0 | 4 | 0 | 0 | 0.00031623 | 3160 | 0 | 4 | 0 | Moderate injuries and/or health effects (e.g. broken bone) | 0 | 0 | 0 | Moderate system degradation (e.g. loss of function, repairable in-situ) | 0 | Repairable in-situ, outside maintenance interval (1 day) [5k USD] | 0
0 | 5 | Very unlikely to occur | 0 | 0.001 | 1000 | 0 | 5 | Major | 0 | 0 | Limited levels of pollution, manageable / moderate effect on environment | 0 | 0 | 0 | Repairable in-situ, outside maintenance interval (1 week) [15k USD] | 0
0 | 6 | 0 | 0 | 0.0031623 | 316 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | Major system degradation or loss of operation for 1 month | 0 | [25k USD] | 0
0 | 7 | Rarely expected to occur | 0 | 0.01 | 100 | 0 | 7 | Critical | Hospitalization (with full recovery) | 0 | Moderate pollution (some clean-up costs) / Serious effect on environment | 0 | Major system degradation or loss of operation for 3 months | 0 | Dry dock required for repair [50k USD] | 0
0 | 8 | 0 | 0 | 0.031623 | 31.6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | Critical system degradation or loss of operation for 6 months | 0 | [150k USD] | 0
0 | 9 | One or more during 20 yr lifetime | 0 | 0.1 | 10 | 0 | 9 | Catastrophic | Hospitalization (with lasting disabilities) | 0 | Major pollution (significant clean-up costs) / disastrous effects on the environment | 0 | Failure to generate power for remainder of project, complete failure | 0 | Loss of device [500k USD] | 0
0 | 10 | 0 | 0 | 0.31623 | 3.16 | 0 | 10 | 0 | A fatality | 0 | 0 | 0 | 0 | 0 | 0 | 0