## Intro
Version: | 1 | Updated: | 2021-02-01
Project Name and Overview
CalWave Design for PacWave
Risk Register Template Introduction:
This risk register template is a companion to the MHK Technology Development Risk Management Framework document. The terminology used in this template is further defined within the framework document. The purpose of this risk register template is to be a tool for identifying risks, analyzing risks, and planning risk responses. As appropriate, this template should be customized by the user to improve its use for their application. The user should add/modify valid data options with the "valid data fields" worksheet by following the procedure on that worksheet (e.g., risk owners "owner" must be modified for each project). Row 3 of the risk "Risk Register" worksheet provides filter options for viewing risk register data; the data can be filtered and reordered using these filter options.
Link to MHK Technology Development Risk Management Framework report
MHK risk register based on template, version: September 23, 2015

## Risk Register
IDENTIFY RISKS PROCESS | [7 empty] | ANALYZE RISKS PROCESS | [5 empty] | RISK RESPONSE PROCESS--STRATEGY & TIMING |  |  | RISK RESPONSE PROCESS--RESIDUAL RISK | [5 empty] | CONTINGENCY PLAN
| RBS |  |  |  |  | Technology Life Phase | Risk Owner | Baseline Risk (before response) | [5 empty] | Risk Response |  |  | Residual Risk (after response) | [5 empty] | Contingency Plan (as if the risk has occurred)
Revision Date | RBS Level 1 | RBS Level 2 | Risk Name | TRL | TPL |  |  | + - | TYP | SEV | FRQ | RPN | Description (with assumptions) | Strategy | Description (with assumptions); incude Timing and Triggers | Response Timing | SEV | FRQ | RPN | Description (with assumptions) | Secondary Risks Resulting From Risk Response | Recommendations & Action Items
2021-02-01 | External | 4.9 External stakeholder | Project delay due to external stakeholders | All | All | Specification | Dan Petcovic | - | T | 3 | 5 | 15 | Several systems involve integration of potentially large and complex components that will require time consuming iterative design loops | mitigate | Work with industry partners early in design process to specify components that are available off the shelf or at relatively shorter lead time | continually | 3 | 4 | 12 | Residual risk that some components will have significant changes in cost or specifications/availability between design iterations | Engaging partners very early in design process and without detailed specifications can lead to supplier fatigue and eventual disinterest | Continually engage suppliers in longer term scope and potential for wave energy generation | Continually update project schedule and identify stakeholder of any anticipated delays
2021-02-01 | Management | 2.1 Project management | Project delay due to internal design decision process | All | All | Design | Marcus Lehmann | - | T | 4 | 4 | 16 | Difficult design decisions will have to be made with less than optimal input information, leading to potential project delays in efforts to obtain further details | mitigate | Utilize established (and/or introduce new) internal processes for decision making, including determining of balance between technical/commercial feasibility and if/what capacity exists to obtain further information | before specification | 4 | 3 | 12 | Residual risk that certain design decision(s) will require additional input that beyond scope/cost of project | Cost overrun could come from delayed deisgn decisions due to staff hours | Proactively engage external network of experts to support design decision reviews, both in terms of technical and commercial viability | Raise additional funding for adjacent project to obtain necessary design input
2021-02-01 | Management | 2.6 Funding | Budget overrun | All | All | Multiple (or all) life phases | Nigel Kojimoto | - | C | 3 | 4 | 12 | Project budget not sufficient to complete requirements | mitigate | Work with industry partners and obtain supplier quotes as early as possible to identify potential unexpected high cost items. Ensure all contracts with design support contractors have strict not-to-exceed budgets | before design finalized | 2 | 3 | 6 | Residual risk that one or more partner/vendor will overrun agreed contract | Potential for relationship impacts with partners if/when refusal to pay for cost overruns not agreed in advance | Engage multiple suppliers to get competitive quotes and look at whole system prior to placing orders | Do not place orders for high value items until reviewed in context of total project, and strict not to exceed terms are discussed and understood
2021-02-01 | Technical | 1.7 System reliability | Voltage flicker exceeds grid interconnection requirements | 6 | 8 | Normal power production | Bryan Murray | - | Q | 3 | 4 | 12 | Inability to decrease peak to average power with advanced controls leading to poor performance of system resulting in inability to maintain stable voltage at grid interface | mitigate | Develop winch-to-wire electrical modeling early in design phase to indentify permissible bounds export current and/or grid-side inverter requirements | before design finalized | 3 | 3 | 9 | Residual risk that model implimentation performs poorly compared to models when implimented in WEC | Reduction in efficient use of CAPEX leading to reduced LCOE | Leverage lessons learned from closed loop control testing in previous projects and PTO testing in FOA 1837 | Increase DC Link energy storage on WEC. Incorporate reactive power correction at the Point of Common Coupling.
2021-02-01 | Technical | 1.7 System reliability | Harmonics exceeding grid interconnection requirements | 6 | 8 | Normal power production | Bryan Murray | - | Q | 3 | 4 | 12 | Inability to efficiently manage reactive loading in the electrical export system | mitigate | Co-design of advanced controls, validated in modelling in concert with applicable standards review, with particular focus on inverters and transformers | before design finalized | 3 | 3 | 9 | Residual risk that model implimentation performs poorly compared to models when implimented in WEC | Reduction in efficient use of CAPEX leading to reduced LCOE | Leverage lessons learned from closed loop control testing in previous projects and PTO testing in FOA 1837 | Introduce filters at the Point of Common Coupling
2021-02-01 | Technical | 1.6 Technical interfaces | Anchor system not within permit bounds | NA | NA | Normal power production | Dan Petcovic | - | Q | 4 | 3 | 12 | Anchor system designed for use at PacWave is unable to obtain necessary permits for deployment | mitigate | Review PacWave permitting limitations and engage with PacWave staff at defined intervals to ensure all stakeholder are aware of anchor design prior to progressing to detailed design | before design finalized | 3 | 2 | 6 | Residual risk that upon completion of detailed design unanticipated changes to anchoring requirements or permitting allowance | Additional unanticipated cost in follow on project | Engage NREL and external experise in anchor design | Maintain design decision notes during design evolution in the case there is a need to change to an alternate design
2021-02-01 | Commercial | 3.3 Suppliers and vendors | Anchor system not economically feasible to deploy | NA | NA | Maintenance | Dan Petcovic | - | C | 3 | 4 | 12 | Inability to capture all associated costs for fabrication and installation of anchoring system, leading to potentially significant unanticipated costs during follow-on PacWave deployment project | mitigate | Engage suppliers as well as offshore operators familiar with the local area to ensure a full understanding of costs in both fabrication and deployment | before design finalized | 3 | 3 | 9 | Residual risk that sufficient funding is obtained to fabricate/deploy anchor in follow on project, but design is not optimized to realize competitive LCOE | Additional unanticipated cost in follow on project | Ensure operational partners are fully engaged in design process | Look for multiple options for anchor systems and deployment methodologies
2021-02-01 | Technical | 1.8 Performance | High friction on seals | 9 | 5 | Normal power production | Nigel Kojimoto | - | C | 2 | 5 | 10 | Higher than anticipated seal friction leads to heat generation and power loss (reduced conversion efficiency) | mitigate | Engage suppliers and perform seal characterization on PTO test bench to validate seal friction requirements and look for opportunities to reduce cylinder travel | before design finalized | 2 | 4 | 8 | Residual risk that upon completion of project adequate sealing solution is not found to sufficiently maintain low seal friction | Reduced conversion efficiency leading to increased LCOE | Further engage suppliers on alternate sealing solutions | Introduce control stategies that minimize stiction (e.g. deadband gains)
2021-02-01 | Technical | 1.3 Estimates, assumptions, constraints | High loads on structural components | 3 | 8 | Specification | Nigel Kojimoto | - | P | 4 | 3 | 12 | Structual loads lead to unacceptable wall thickness and corresponding LCOE | mitigate | Estimate loads early in design process and work with testing partner to develop test procedure for higher risk structural components | before design finalized | 3 | 3 | 9 | Not feasibly able to develop test procedure to validate higher risk structural components within project budget | Additional funding needed to validate structural component loads | Perform adequate CFD | Reduce pressure hull volume.
2021-02-01 | Management | 2.2 Program/Portfolio management | Multitasking between projects | NA | NA | Multiple (or all) life phases | Marcus Lehmann | - | T | 3 | 4 | 12 | Staff and partners cannot efficiently mange time between multiple parallel projects, leading to program delays | mitigate | Continue to align project schedule with other on-going projects and staff allocations; ensure partners are doing the same | continually | 2 | 3 | 6 | Delays in other projects could pull resources | Project delays, cost overruns if delays cascade into inefficient use of vendors | Weekly cross project status updates | Inform DOE management and partners of any potential delays before they occur
2021-02-01 | Technical | 1.7 System reliability | Fatigue loads on moving parts | 7 | 7 | Normal power production | Nigel Kojimoto | - | Q | 3 | 4 | 12 | Final design does not adequatly account for fatigue loading during extended lifetime deployments | avoid | Review standards and work with expert partners to ensure full understanding of fatigue cycle impications. Identify any feasible laboratory-based fatigue testing | before design finalized | 2 | 3 | 6 | Fatigue modelling does not accuratly represent failure modes | Additional need for fatigue testing | Anticipate if need arises for additional funding for fatigue testing beyond the scope of this project | Raise additional funding for fatigue testing
2021-02-01 | Technical | 1.6 Technical interfaces | Controls integration | 4 | 8 | Assembly and commissioning | Thomas Boerner | - | Q | 4 | 3 | 12 | Advanced controls integration fails to adequatly control system, leading to inability to complete performance evaluation | mitigate | Fully characterize individual components prior to integrating system in model; validate advance controls in numerical modelling | before assembly and commissioning | 3 | 2 | 6 | Residual risk of delaying performance testing due to controls integration issues | Project delays and decreased performance | Incorporate lessons learned from closed loop testing in previous projects | Complete testing with less than optimized controls
2021-02-01 | Technical | 1.9 Safety | Safety of personnel working at or near test setup | NA | NA | Multiple (or all) life phases | Marcus Lehmann | - | S | 5 | 3 | 15 | Potential risk of personnel safety due to electrical shock, trips, slips, falls, pinch points, lifting operations, and pressurized hydraulic and rotating systems | mitigate | Comprehensive health and safety planning and employee training, use of standard and emergency operating procedures | continually | 5 | 2 | 10 | Impossible to entirely remove risk of safety to personnel working with rotating, energized, and pressurized systems | Personnel safety | Continual review of health and safety procedures and standard and emergency operating procedures | Emergency response plans in place at test facility
2021-02-01 | Technical | 1.9 Safety | Damage to equipment on PTO test bench | NA | NA | Multiple (or all) life phases | Thomas Boerner | - | S | 4 | 3 | 12 | Potential risk of equipment damage due to incorrect assembly or mechanical failure | mitigate | Establishment and adherence to standard and emergency operating procedures | before assembly and commissioning | 3 | 2 | 6 | Impossible to entirely remove risk of damage to equipment working with integrated rotating, energized, and pressurized systems | Equipment damage | Continual review of equipment operating procedures and staff training | Emergency response plans in place at test facility
2021-02-01 | External | 4.9 External stakeholder | Data security | NA | NA | Multiple (or all) life phases | Thomas Boerner | - | S | 4 | 3 | 12 | Secure storage and transmission of sensitive intellectual property required during project poses risk of data being inadvertantly or malicously (via hacking) released | mitigate | Establishment and adherence to data protection procedures and use of nondisclosure agreements | continually | 3 | 2 | 6 | Impossible to entirely remove risk of release of proprietary information | Business losses | Continual review and updating of data security policies and systems | Ensure patent protection in place where possible
2021-02-01 | Commercial | 3.7 LCOE | Inaccurate cost estimating | All | All | Multiple (or all) life phases | Marcus Lehmann | - | C | 4 | 3 | 12 | Inaccurate/optimistic cost estimating for 2-year deployment at PacWave leads to underfunded execution project | avoid | Work with partners and vendors to ensure adequate and fully informed cost estimates for both fabrication and deployment | continually | 4 | 3 | 12 | Impossible to entirely remove risk of suppliers providing optimistic estimates or internal modelling using optimistic assumptions | Reduced LCOE | Calculate LCOE both forwards and backwards, continually updating with supplier input | Maintain communication with potential sources of additional funding
2021-02-01 | Commercial | 3.7 LCOE | Competitive LCOE of designed system | All | All | Multiple (or all) life phases | Marcus Lehmann | - | C | 3 | 3 | 9 | System designed in project does not result in a path to competitive LCOE | avoid | Ensure to include LCOE calculations in all component and subsystem design decisions | continually | 3 | 3 | 9 | Residual risk that assumptions on cost implications of design decisions were optimistic or not inclusive of all associated costs (particularly with respect to IO&M) | Additional cost to complete PacWave deployment | Work with partners and suppliers to identify alternatives to any components/subsystems that do not achieve LCOE targets | Evolve commercialization plan and LCOE learning rates to best prepare for a difficult decision on proceeding with PacWave deployment if sub-optimal LCOE forecasting occurs
2021-02-01 | Commercial | 3.7 LCOE | Commercial viability of designed system | All | All | Multiple (or all) life phases | Marcus Lehmann | - | C | 4 | 3 | 12 | System designed in project does not have adequate commercial potential | avoid | Work with initial deployment partners to fully understand minimum viable product for first commercial deployments | continually | 4 | 3 | 12 | Residual risk that project budget/timeline and anticipated next project (PacWave deployment) budget/timeline require designing system that does not produce sufficient power to achieve commercial viability | Need to deploy subsequent larger scale system at PacWave prior to deploying commercial system | Engage with initial customers throughout project to ensure requirements are understood | Calculate/investigate fund raising required for additional design evolution/scale up prior to funding from commercial customer
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0

## Summary
PRE-MITIGATION
| Severity |  |  |  |  | Total risrs | High | Medium | Low
Freq | 1 | 2 | 3 | 4 | 5 | 18 | 3 | 15 | 0
5 | 0 | 1 | 1 | 0 | 0 |  | 16.67% | 83.33% | 0%
4 | 0 | 0 | 6 | 1 | 0
3 | 0 | 0 | 1 | 7 | 1
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0
POST-MITIGATION
| Severity |  |  |  |  | Total risks | High | Medium | Low
Freq | 1 | 2 | 3 | 4 | 5 | 18 | 0 | 11 | 7
5 | 0 | 0 | 0 | 0 | 0 |  | 0% | 61.11% | 38.89%
4 | 0 | 1 | 1 | 0 | 0
3 | 0 | 3 | 5 | 3 | 0
2 | 0 | 0 | 4 | 0 | 1
1 | 0 | 0 | 0 | 0 | 0
MITIGATION RESULTS
| Severity |  |  |  |  | Total risks | High | Medium | Low
Freq | 1 | 2 | 3 | 4 | 5 | 0 | -3 | -4 | 7
5 | 0 | -1 | -1 | 0 | 0
4 | 0 | 1 | -5 | -1 | 0
3 | 0 | 3 | 4 | -4 | -1
2 | 0 | 0 | 4 | 0 | 1
1 | 0 | 0 | 0 | 0 | 0

## Valid data fields
Important Note: use the following procedure to add/or change valid data fields for this risk register
1) add new data option below appropriate column within "Valid data field" worksheet
2) click (Ctrl+F3), for Name Manager window
3) highlight Name being modified, click "Edit" icon
4) under "Refers to:", extend range to include new data
5) click "OK" icon
6) click "Close" icon
7) new data should now appear as option within "Risk Register" worksheet
RBS | Technical | Management | Commercial | External | TRL | TPL | Life | Owner | + or - | Type | Severity | Frequency | NegResponse | PosResponse | Timing
Technical | 1.1 Scope definition | 2.1 Project management | 3.1 Contractual terms and conditions | 4.1 Legislation | NA | NA | NA | Marcus Lehmann | - | S | 0 | 0 | avoid | exploit | now
Management | 1.2 Requirements definition | 2.2 Program/Portfolio management | 3.2 Internal procurement | 4.2 Exchange rates | All | All | Multiple (or all) life phases | Bryan Murray | + | C | 1 | 1 | transfer | share | continually
Commercial | 1.3 Estimates, assumptions, constraints | 2.3 Operations management | 3.3 Suppliers and vendors | 4.3 Site/facilities | 1 | 1 | Specification | Nigel Kojimoto |  | T | 2 | 2 | mitigate | enhance | before specification
External | 1.4 Technical processes | 2.4 Organization | 3.4 Subcontracts | 4.4 Environmental/weather | 2 | 2 | Design | Thomas Boerner |  | P | 3 | 3 | accept | accept | before design finalized
| 1.5 Technology | 2.5 Human resourcing | 3.5 Client/customer stability | 4.5 Competition | 3 | 3 | Manufacturing | Dan Petcovic |  | Q | 4 | 4 |  |  | before PO issued
| 1.6 Technical interfaces | 2.6 Funding | 3.6 Partnerships and joint ventures | 4.6 Regulatory | 4 | 4 | Transportation | Josiah Clark |  | E | 5 | 5 |  |  | before manufacturing
| 1.7 System reliability | 2.7 Communication | 3.7 LCOE | 4.7 Political | 5 | 5 | Assembly and commissioning |  |  | R |  |  |  |  | before assembly and commissioning
| 1.8 Performance | 2.8 Information |  | 4.8 Force majeure | 6 | 6 | Normal power production | [7 empty] | before decommissioning
| 1.9 Safety | 2.9 Quality |  | 4.9 External stakeholder | 7 | 7 | Extreme events | [7 empty] | January
| 1.10 Security | 2.10 Reputation |  |  | 8 | 8 | Faults | [7 empty] | February
[5 empty] | 9 | 9 | Maintenance | [7 empty] | March
[7 empty] | Repair | [7 empty] | April
[7 empty] | Decommissioning | [7 empty] | May
June
July
August
September
October
November
December