## Schedule
ORIGINAL SCHEDULE
| Task | Time (hrs) | Notes
2021-11-29 | Setup and Fill tank | 8 | Install
2021-11-30 | Splashdown | 8 | Check device ballasting, overall system. Verify pre-load values.
2021-12-01 | Shakedown/Calibrate | 8 | Run Regular waves, rough in range of damping and spring, check calibration/ramps/press. Sensors etc.
2021-12-02 | SID 60th and 7:60 scale, no waves | 8 | SID No Waves Pink Multisine from PTO at 60th scale range, 0.25hz to 2 hz pink spectrum, 200 seconds, at 7:60 scale range, 0.1hz to 1.2 hz pink spectrum, 200 seconds
2021-12-03 | SID 60th and 7:60 scale, with waves | 8 | SID With Waves Pink Multisine from PTO and Wavemaker at 60th scale range, 0.25hz to 2 hz pink spectrum, 200 seconds, at 7:60 scale range, 0.1hz to 1.2 hz pink spectrum, 200 seconds
| Task | Time (hrs) | Notes
2021-12-06 | Remaining SID | 8 | Any remaining SID runs
2021-12-07 | 60th regular waves | 8 | Check device ballasting, overall system. Verify pre-load values./ heave free decay tests
2021-12-08 | 60th regular/iregular | 8 | Regular wave parameter sweep
2021-12-09 | 60th iregular | 8 | Regular/Iregular wave parameter sweep
2021-12-10 | 7:60 regular waves | 8 | Iregular wave parameter sweep
| Task | Time (hrs) | Notes
2021-12-13 | 7:60 regular/iregular | 8 | Regular/Iregular wave parameter sweep
2021-12-14 | 7:60 iregular | 8 | Iregular wave parameter sweep
2021-12-15 | any makeup waves | 8 | any makeupe parameter sweeps waves
2021-12-16 | free decay tests/removal | 8 | free decay tests/ any other tests/removal/towing in waves tests
NEW SCHEDULE
| Task | Time (hrs) | Notes
2021-12-06 | 7:60 regular waves | 8 | Irregular wave parameter sweep
2021-12-07 | 7:60 regular waves/60th scale regular tuning | 8 | Irregular wave parameter sweep/regular wave tuning for 60th scale
2021-12-08 | 60th irregular | 8 | Regular/Iregular wave parameter sweep
2021-12-09 | 60th irregular | 8 | Regular/Iregular wave parameter sweep
2021-12-10 | SID 60th and 7:60 scale, with waves | 8 | SID With Waves Pink Multisine from PTO and Wavemaker at 60th scale range, 0.25hz to 2 hz pink spectrum, 200 seconds, at 7:60 scale range, 0.1hz to 1.2 hz pink spectrum, 200 seconds
| Task | Time (hrs) | Notes
2021-12-13 | any makeup waves | 8 | any makeup parameter sweeps waves
2021-12-14 | free decay tests/removal | 8 | free decay tests/ any other tests/removal/towing in waves tests
2021-12-15 | Large wave tests for ULS | 8 | Large regular waves for ULS tests
2021-12-16 | Final day/Removal | 8 | Any makeup waves

## Device Configurations
Configuration | Fins | Pre-Tension | Mooring Line Swivels
Configuration 1 | Single Rear Fin | Center of Cylinder | no swivels
Configuration 2 | Single Rear Fin | Center of Cylinder | added 2 swivels
Configuration 3 | 4 fins | Center of Cylinder | 2 swivels

## Waves Reference
AquaHarmonics TEAMER test Matrix |  |  |  | Tp (T) | Hs (H)
Tank Scale | Type | Number | Wave # | (s) | (m)
1:60 scale | IWS (JONSWAP) | 1 | IWS 1 | 0.95311 | 0.03978 | PTO friction too high to run | 0.25hz to 2 hz pink spectrum
|  | 2 | IWS 2 | 1.2856 | 0.04488 | PTO friction too high to run
|  | 3 | IWS 3 | 1.502 | 0.09112
|  | 4 | IWS 4 | 1.6572 | 0.03485 | PTO friction too high to run
|  | 5 | IWS 5 | 1.9857 | 0.09928
|  | 6 | IWS 6 | 2.1513 | 0.05525
| Monochromatic | 7 | Regular Wave | 0.95311 | 0.03978 | PTO friction too high to run
|  | 8 | Regular Wave | 1.2856 | 0.04488 | PTO friction too high to run
|  | 9 | Regular Wave | 1.502 | 0.09112
|  | 10 | Regular Wave | 1.6572 | 0.03485 | PTO friction too high to run
|  | 11 | Regular Wave | 1.9857 | 0.09928
|  | 12 | Regular Wave | 2.1513 | 0.05525
1:60 scale equivelent conditions for 1:7 scale device operating in full scale seas or 7:60 scale | IWS (JONSWAP) | 13 | IWS 1 | 2.4968 | 0.273 |  | 0.1hz to 1.2 hz pink spectrum
|  | 14 | IWS 2 | 3.3678 | 0.308
|  | 15 | IWS 3 | 3.9348 | 0.62533
|  | 16 | IWS 4 | 4.3413 | 0.23917
|  | 17 | IWS 5 | 5.202 | 0.68133
|  | 18 | IWS 6 | 5.6358 | 0.37917
| Monochromatic | 19 | Regular Wave | 2.4968 | 0.273
|  | 20 | Regular Wave | 3.3678 | 0.308
|  | 21 | Regular Wave | 3.9348 | 0.62533
|  | 22 | Regular Wave | 4.3413 | 0.23917
|  | 23 | Regular Wave | 5.202 | 0.68133
|  | 24 | Regular Wave | 5.6358 | 0.37917
7:60 Scale | Extreme (100yr RP) | 25 | 100yr RP 3 | 4.372 | 0.74667 | big kahuna
|  | 26 | 100yr RP 4 | 3.4157 | 0.665 | just right kahuna
|  | 27 | 100yr RP 5 | 2.3807 | 0.47833 | little kahuna
* JONSWAP waves are repeating 200 second segments for 90 minutes
**Monochromatic waves are repeating for 90 minutes
We just have to be careful with the super small and short waves, 0.95 s waves is about the limit of the system.
multisines with no waves
Justification for waves to test
|  |  | Wave # | Tp | Hs
Type | Number | Hawaii |  | (s) | (m)
IWS (JONSWAP) | 13 | 32.8% | IWS 1 | 7.31 | 2.34
| 14 | 24.5% | IWS 2 | 9.86 | 2.64
| 15 | 0.1% | IWS 3 | 11.52 | 5.36
| 16 | 13.3% | IWS 4 | 12.71 | 2.05
| 17 | 0% | IWS 5 | 15.23 | 5.84
| 18 | 1.3% | IWS 6 | 16.5 | 3.25
Type | Number | Wave # | Tp | Hs |  |  | Type | Wave # | Tp | Hs
IWS (JONSWAP) | 13 |  | (s) | (m) |  |  | IWS (JONSWAP) |  | (s) | (m)
| 14 | IWS 1 | 7.31 | 2.34 |  |  |  | IWS 1 | 7.31 | 2.34
| 15 | IWS 2 | 9.86 | 2.64 |  |  |  | IWS 2 | 9.86 | 2.64
| 16 | IWS 3 | 11.52 | 5.36 |  |  |  | IWS 3 | 11.52 | 5.36
| 17 | IWS 4 | 12.71 | 2.05 |  |  |  | IWS 4 | 12.71 | 2.05
| 18 | IWS 5 | 15.23 | 5.84 |  |  |  | IWS 5 | 15.23 | 5.84
|  | IWS 6 | 16.5 | 3.25 |  |  |  | IWS 6 | 16.5 | 3.25

## Failure Modes
Failure modes matrix
|  | EndStop |  | Generator Braking |  | Power Production
Condition | Pre-Load | Spring Rate | Engagement postion | Quadratic Damping (gen braking) | Engagement postion | Linear damping | Negative Spring
5x5 200s repeats
Functional Tests
Test 1 | 2 | 5 steps of 400 to 2000 | 0.25 | steps of 0.6 to max of 3 | 0.15 | 0.15
Test 2 | 2 | 5 steps of 400 to 2000 | 0.3 | steps of 0.6 to max of 3 | 0.2 | 0.15
Test 3 | 2 | 5 steps of 400 to 2000 | 0.35 | steps of 0.6 to max of 3 | 0.25 | 0.15
1000 seconds each
Pre-Load with Endstop only
Test 1 | 2 | 5 steps of 400 to 2000 | 0.25
Test 2 | 2 | 5 steps of 400 to 2000 | 0.3
Test 3 | 2 | 5 steps of 400 to 2000 | 0.35
1000 seconds each
end stop only with absolute position
Test 1 | 0 | 5 steps of 400 to 2000 | 0.25
Test 2 | 0 | 5 steps of 400 to 2000 | 0.3
Test 3 | 0 | 5 steps of 400 to 2000 | 0.35
*absolute position

## ULS Scaling
Scale
0.11667
ULS 100RP storm wave WETS 30m
| Hs | Tp
Full Scale | 6.4 | 12.8
7/60 scale | 0.74667 | 4.372

## 12-1-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | filename | simulink config
1 | 3:10 | 1:60 | No Waves, PTO Multisine | 2Nm | 1.5Nm | No Waves | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times | Ran Through | 1 | 20211201T152420Z | faa8b9
2 | 3:27 | 7:60 | No Waves, PTO Multisine | 2Nm | 2Nm | No Waves | PTO1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | Stopped to increase Pre-Tension | 1
3 | 3:27 | 7:60 | No Waves, PTO Multisine | 2.5Nm | 2Nm | No Waves | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | Ran Through | 1 | 20211201T154720Z | faa8b9
4 | 3:48 | 1:60 | No Waves, PTO Multisine | 2Nm | 0.75Nm | No Waves | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times | Ran Through | 1 | 20211201T160814Z | faa8b9
5 |  | 1:60 | Waves, PTO Multisine | 2Nm | 0.75Nm | Wave 6 Pink Noise, 200s repeating | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times |  |  | 20211201T165756Z | ba9da1

## 12-2-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
1 | 10:11 | 1:60 | ~300 Sec | ~1600 | Waves, PTO Multisine | 2Nm | 0.75Nm | Wave 5 Pink Noise, 200s repeating | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times | 1200 seconds min of repeating 200s | 1 | Use wavemaker signal to start | 20211202T103419Z | b508e6
2 | 10:38 | 1:60 | ~260 | ~1600 | Waves, PTO Multisine | 2.5Nm | 2Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | 1200 seconds min of repeating 200s | 1 | Use wavemaker signal to start | 20211202T111136Z | b508e6
3 |  |  |  |  | PTO Multisine | 2.5 | 2 | N/A | change force feedback controller tuning to 3/1/2 from 1.3/1/1.8 | ~400 seconds of repeating 200s | 1 | Force Start | 20211202T130550Z | b508e6
4 |  |  |  |  | PTO Multisine | 2 | 0.75 | N/A | change force feedback controller tuning to 3/1/2 from 1.3/1/1.8 | ~400 seconds of repeating 200s | 1 | Force Start | 20211202T131740Z | b508e6
5 |  |  |  |  | PTO Multisine | 2.5 | 2 | N/A | change force feedback controller to 1/0/0 (only feed fwd) | ~400 seconds of repeating 200s | 1 | Force Start | 20211202T132824Z | b508e6
6 |  |  |  |  | PTO Multisine | 2 | 0.75 | N/A | change force feedback controller to 1/0/0 (only feed fwd) | ~400 seconds of repeating 200s, almost no movement amp too low | 1 | Force Start | 20211202T133705Z | b508e6
7 |  |  |  |  | PTO Multisine | 2 | 1.5 | N/A | change force feedback controller to 1/0/0 (only feed fwd) | ~400 seconds of repeating 200s | 1 | Force Start | 20211202T134717Z | b508e6
8 |  |  |  |  | Waves, PTO Multisine | 2.5Nm | 2Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | 1200 seconds min of repeating 200s | Add Swivel | Use wavemaker signal to start | 20211202T163340Z | b508e6
[5 empty] | Waves, PTO Multisine | 2.5Nm | 2Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | 1200 seconds min of repeating 200s | Remove Fin | Use wavemaker signal to start | 20211202T171235Z | b508e6

## 12-3-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
9 |  |  |  |  | Drop test | N/A | N/A | N/A | N/A | No PTO Manual Drop | 4 fins | N/A | 20211203T085909Z | b508e6
10 |  |  |  |  | Drop test | N/A | N/A | N/A | N/A | No PTO Manual Drop | 4 fins | N/A | 20211203T090016Z | b508e6
11 |  |  |  |  | Drop test | N/A | N/A | N/A | N/A | No PTO Manual Drop | 4 fins | N/A | 20211203T090119Z | b508e6
12 |  |  |  |  | Waves, PTO Multisine | 2.5Nm | 2Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times | 1200 seconds min of repeating 200s | 4 fins | Use wavemaker signal to start | 20211203T093928Z | b508e6
13 |  | 7:60 |  |  | regular waves | 2.5 | N/A | Wave 22, regular | Manual Tuning in reg waves | found convention kp neg for damping. -.5 max, kl +, range +.4 max | 4 fins | Manual | 20211203T101040Z | b508e6
14 |  | 7:60 |  |  | regular waves | 2 |  | Wave 9, regular | Manual Tuning in reg waves | limits: -.1 damp, .5 spr | 4 fins | Manual | 20211203T103847Z | 16afb6
15 |  |  |  |  | regular waves | 2.5 |  | Wave 22, regular | Manual Tuning in reg waves | manual tuning and parameter sweep test | 4 fins | Manual | 20211203T122557Z | ad7cb3
16 |  |  |  |  | irregular | 2.5 |  | Wave 13, irregular | kp = [.06,.12,.18,.24,.3] ki = [0, -.1,-.2,-.3,-.4] | parameter sweep | 4 fins | wavemaker | 20211203T145244Z | 924485
17 |  |  |  |  | irregular | 2.5 |  | Wave 14, irregular | kp = [.05,.10,.15,.20,.25] ki = [0, -.1,-.2,-.3,-.4] | parameter sweep | 4 fins | wavemaker | 20211203T170314Z | 8b549b

## 12-6-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
18 | 9:45 | 7_60 |  |  | irregular | 2.5 |  | Wave 14, irregular | kp = [.02, .04, .06, .08 .10,] ki = [0, -.08,-.16,-.24,-.32] | parameter sweep, limited motor travel | 4 fins | wavemaker | 20211206T111702Z | 0f74c2
19 |  | 7_60 |  |  | ramp/calibration check | 2.5/3 |  | none |  | several ramps, .5 offset with ramp amplitude 3. without offset windup occured and torque tracking was poor |  |  | 20211206T112359Z
20 |  | 7_60 |  |  | irregular | 2.5 |  | Wave 13, irregular | kp = [.02, .04, .06, .08 .10,] ki = [0, -.08,-.16,-.24,-.32] | limited motor travel |  |  | 20211206T130016Z
21 |  | 7_60 |  |  | irregular |  |  | Wave 13, irregular | kp = [.02, .04, .06, .08 .10,] ki = [0, -.1,-.2,-.3,-.4] | shortened mooring line, hoping to fix limited motor travel. sufficient damping, could have gone higher on spring
22 | [7 empty] | 15 |  | cut parameter sweep short, was getting too crazy. turned off negative spring and added big damping to get a feel for big wave survival. went to .25 and .35 damping manually | removed ballast |  | 20211206T172223Z | 6c54ae

## 12-7-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
23 |  | 7_60 |  |  | irregular | -2.5 |  | Wave 16, irregular | 2.5 | kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75) 3000lb mooring line signal dropped out at some point, best power at highest damping, 2nd highest spring | 4 fins, lower ballast |  | 20211207T103205Z | 6c54ae
24 |  | 7_60 |  |  | irregular | -2.5 |  | wave 13,irregular | 2.5 | kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), sweep finds peak power | 4 fins, lower ballast |  | 20211207T120758Z
25 |  |  |  |  | ramp |  |  | ramps |  |  | 4 fins, lower ballast |  | 20211207T121536Z
26 |  | 7_60 |  |  | irregular | -2.5 |  | wave 14, irregular | 2.5 | kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), peak power barely | 4 fins, lower ballast |  | 20211207T140339Z
27 |  | 7_60 |  |  | irregular | -2.5 |  | wave 18, irregular | 2.5 | kp = [.08, .16, .24, .32, .4,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), | 4 fins, lower ballast |  | 20211207T154814Z
28 |  | 7_60 |  |  | irregular | -2.5 |  | wave 14, irregular | 2.5 | kp = [.08, .16, .24, .32, .4,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), peak power clearly | 4 fins, lower ballast |  | 20211207T172133Z
29 |  |  |  |  | ramp |  |  | ramps |  |  |  |  | 20211207T172558Z
31 |  |  |  |  | heave decay |  |  | heave decay | preload 5nm | preloaded 5nm and disabled PTO |  |  | 20211207T172904Z
32 |  |  |  |  | heave decay |  |  | heave decay | preload 4nm | preloaded 4nm and disabled PTO |  |  | 20211207T173220Z
33 |  |  |  |  | heave decay |  |  | heave decay | preload 3 nm | preloaded 3nm and disabled PTO |  |  | 20211207T173432Z
34 |  |  |  |  | heave decay |  |  | heave decay | preload 2 nm | preloaded 2nm and disabled PTO |  |  | 20211207T173610Z
35 |  |  |  |  | heave decay |  |  | heave decay | preload 1nm, 1.5nm | preloaded 1nm and 1.5nm and disabled PTO repeated below at 1.5nm since this was not great.
36 |  |  |  |  | heave decay |  |  |  | preload 1.5nm | preloaded 1.5nm and disabled PTO |  |  | 20211207T173938Z

## 12-8-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
37 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211208T085957Z
38 |  | 1_60 |  |  | regular | varies |  | wave 7 regular |  | Determine Ki and Kp, preload. Seastate too small to overcome PTO internal friction, disabled PTO IMU shows relevant motion | 4 fins, lower ballast |  | 20211208T091736Z | 6c54ae
39 |  | 1_60 |  |  | regular | varies |  | wave 11 regular |  | Determine Ki and Kp, preload. limits found .45 neg spring, .15 damping. 1.2 preload | 4 fins, lower ballast |  | 20211208T093939Z
40 |  | 1_60 |  |  | regular | varies |  | wave 12 regular |  | Determine Ki and Kp, preload. .5 neg spring, .075 damping 1.2 preload | 4 fins, lower ballast |  | 20211208T095716Z
41 |  | 1_60 |  |  | regular | varies |  | wave 9 regular |  | Determine Ki and Kp, preload. .5 neg spring, .075 damping 1.2 preload | 4 fins, lower ballast |  | 20211208T101503Z
42 |  |  |  |  | ramp |  |  | Ramp Test |  |  | 4 fins, lower ballast |  | 20211208T115517Z
43 |  | 1_60 |  |  | irregular | -1.2 |  | wave 3, irregular |  | kp = [.015, .03, .045, .06, .075,] ki = [0, -.125,-.25.-.375,.5](0.625) preload 1.2. best power at kp=0.015, could have used lower damping range | 4 fins, lower ballast |  | 20211208T114949Z
44 |  | 1_60 |  |  | irregular | -1.2 |  | wave 5, irregular |  | kp = [.024, .048, .072, .096, .12,] ki = [0, -.1125,-.225.-.3375,-.45](0.5625) preload 1.2 | 4 fins, lower ballast |  | 20211208T132937Z
45 |  | 1_60 |  |  | irregular | -1.2 |  | wave 6, irregular |  | kp = [.015, .03, .045, .06, .075,] ki = [0, -.125,-.25.-.375,.5](0.625) preload 1.2 | 4 fins, lower ballast |  | 20211208T150439Z
46 |  | 1_60 |  |  | irregular | -1.2 |  | wave 3, irregular |  | kp = [.003, .006, .009, .012, .015,] ki = [0, -.125,-.25.-.375,.5](0.625) preload 1.2 | 4 fins, lower ballast |  | 20211208T164423Z
47 | [7 empty] | Ramp Test |  |  |  |  | 20211208T165019Z
kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75),
kp = [.08, .16, .24, .32, .4,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75),

## 12-9-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
37 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211209T132915Z
38 |  |  |  |  | wave 13,irregular | 2.5 |  |  |  | kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), WITH endstops, power limit 27 watts, generator braking at .25 m |  |  | 20211209T150530Z
39 |  |  |  |  | wave 13,irregular | 2.5 |  |  |  | kp = [.05, .1, .15, .2, .25,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), WITH endstops, power limit 27 watts, generator braking at .25 m AND unidirectional damping |  |  | 20211209T171418Z | 8e840e
wave 15

## 12-10-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
40 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211210T085551Z | 8oc6ob
41 | [7 empty] | Wave 17, "IWS 5" |  | kp = [.05, .1, .15, .2, .25,] ki = [0, 0.0875 0.1750 0.2625 0.3500] (spring gain .4375), WITH endstops, power limit 27 watts, generator braking at .25 m AND unidirectional damping). max power at highest damping and 3/4 highest spring |  |  | 20211210T103454Z
42 | [7 empty] | Wave 14, "IWS 2" |  | kp = [.08, .16, .24, .32, .4,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), best performance highest damping and -.45 spring |  |  | 20211210T121858Z
43 | [7 empty] | Wave 16, "IWS 4" |  | kp = [.08, .16, .24, .32, .4,] ki = [0, -.15,-.3,-.45,-.6] (spring gain .75), |  |  | 20211210T140115Z
44 | [7 empty] | Wave 15, "IWS3" |  | kp = [.12, .24, .36, .48, .6,] ki = [0, -0.0750 - 0.1500 - 0.2250 -0.3000] (spring gain -.3750),. peak power in middle of range |  |  | 20211210T154133Z
45 | [7 empty] | Wave 18 "IWS 6" |  | kp = [.12, .24, .36, .48, .6,] ki = [0, 0.0875 0.1750 0.2625 0.3500] (spring gain .4375) |  |  | 20211210T172559Z

## 12-13-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
46 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211213T094052Z | 8oc6ob
47 | [5 empty] | 2.5Nm | 2Nm | No Waves | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T100715Z
48 | [5 empty] | 2Nm | 0.75Nm | No Waves | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T103303Z
49 | [7 empty] | Wave 18 "IWS 6" |  | kp = [ 0.1050 0.2100 0.3150 0.4200 0.5250] ki = [ 0 0.1800 0.3600 0.5400 0.7200 ]( 0.9000) |  |  | 20211213T122917Z
50 | [5 empty] | 2Nm | 0.75Nm | Wave 6 Pink Noise, 200s repeating | PTO 1000s multisine, 0.25hz to 2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T130701Z
51 | [5 empty] | 2.5Nm | 2Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T133132Z
52 | [5 empty] | 2.5Nm | 1.25Nm | Wave 16 Pink Noise, 200s repeating | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T141328Z
53 | [5 empty] | 2.5Nm | 1.25Nm | No Waves | PTO 1000s multisine, 0.1hz to 1.2 hz pink spectrum, 200 seconds, repeated 5 times |  |  |  | 20211213T143722Z
54 | [5 empty] | 2.5 | 0 | Chirp | Preload only |  |  |  | 20211213T163509Z
55 | [7 empty] | Ramp test |  |  |  |  | 20211213T170029Z

## 12-14-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
56 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211214T085623Z | af6ca1
57 | [7 empty] | 27 |  | free form tuning in steep waves. high damping, low damping, no damping, no generator braking, no preload |  |  | 20211214T085623Z
58 | [7 empty] | ramp test |  |  |  |  | 20211214T105656Z
59 | [7 empty] | Big Kahuna |  | increased PTO force limit from 6 to 10 nm to be able to simulate endstop spring without saturating |  |  | 20211214T113930Z
60 | [7 empty] | Big Kahuna |  | limit parameter sweep 1 |  |  | 20211214T150339Z
61 | [7 empty] | Big Kahuna |  | limit parameter sweep 2. genbrake at .2m endstop at .3m |  |  | 20211214T164430Z
62 | [9 empty] | ramp |  |  | 20211214T165142Z

## 12-15-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
56 |  |  |  |  | ramp |  |  | Ramp test |  |  |  |  | 20211215T090129Z | af6ca1
57 | [9 empty] | limit parameter sweep, endstops at .25 / .35 m |  |  | 20211215T105512Z
58 | [9 empty] | no damping, preload + endstop |  |  | 20211215T115525Z
59 | [9 empty] | no damping, preload + endstop .3 |  |  | 20211215T123924Z
60 | [9 empty] | no damping, preload + endstop .35 |  |  | 20211215T131530Z
61 | [9 empty] | no damping or preload, endstop .25 |  |  | 20211215T144545Z
62 | [9 empty] | no damping or preload, endstop .3 |  |  | 20211215T151121Z
63 | [9 empty] | no damping or preload, endstop .35. 2 repetititions of param sweep, 1st had preload left on |  |  | 20211215T154900Z
64 | [9 empty] | ramp test |  |  | 20211215T155601Z

## 12-16-21
Wednesday 12-1-2021
Run | Apprx. Time | Scale | Start Sim | End Sim | Type | Pre-Tension/Offset | Amplitude | Waves Notes | PTO Notes | Run Notes | Device Configuration | Controller start | filename | simulink config
65 | [7 empty] | None |  | Ramp Test |  |  | 20211216T091100Z | 20211216T091100Z
66 | [7 empty] | Wave 19, regular |  | 12.5 s parameter sweep. Kp = .04 to .4. Ki = [ 0 0.0667 0.1333 0.2000 0.2667 0.3333 0.4000 0.4667 0.5333 0.6000] Swivel Broke |  |  | 20211216T095326Z
[10 empty] | Ramp Test |  |  | 20211216T095822Z
[8 empty] | Wave 19, regular |  | 12.5 s parameter sweep. Kp = .04 to .4. Ki = [ 0 0.0667 0.1333 0.2000 0.2667 0.3333 0.4000 0.4667 0.5333 0.6000] |  |  | 20211216T102627Z
[8 empty] | Wave 20, regular |  | 16.85 s parameter sweep. Kp = .06 to .6. Ki = [ 0 0.0667 0.1333 0.2000 0.2667 0.3333 0.4000 0.4667 0.5333 0.6000] |  |  | 20211216T110846Z
[8 empty] | Wave 21, regular |  | 19.65 s parameter sweep. Kp = .06 to .6. Ki = [ 0.0400 0.0800 0.1200 0.1600 0.2000 0.2400 0.2800 0.3200 0.3600] (.4), line broke |  |  | 20211216T113921Z
[8 empty] | none |  | calm water towing |  |  | 20211216T122202Z
[8 empty] | wave 16 |  | towing |  |  | 20211216T123739Z