## Table_1
Table 1. Break-down of project tasks, the number of cases, and timeline for each task.
Task | Case details | Number of cases | Time cost (week) | Note
A. Grid-size time-step convergence test | Test baseline design with a 3 x 3 grid-size and time-step matrix | 9 | 6 | The best setup will be adopted for next tasks
B. Damping torque curves testing | Test two more damping torque curves on the baseline design | 2 | 1.5 | Settle on one damping torque curve for all subsequent cases
C. Test the Rhinoceros3D automated geometry generation script | The script is intended to automate the geometry generation of the main part of the turbine as shown in Figure 3 | N/A | 1.5
D. CFD for combinations of chord length and horizontal semi-axis | 3 chord lengths; 4 horizontal semi-axis levels | 12 | 8 | Only the best design proceeds to next steps
of the guide curve
E. CFD for different immersion levels | 3 additional immersion levels | 3 | 2 | Only the best design proceeds to next steps
G. Summary of power performance for all designs | Present the comparison of power performance for all designs investigated | N/A | 1
H. Reporting | Final report |  | 2
Total |  | 26 | 22