## Het 5a
Test Description | Period(s) [s] | Amplitude(s) [m] | Wave Heading(s) [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | 1.39 | 0.03 | 0 | 1b | 2 | 2025-04-02 | 1
|  |  | 15 | 1d |  | 2025-04-02 | 2
|  |  | 30 | 1e |  | 2025-04-02 | 3
| 1.2 | 0.03 | 0 | 2b |  | 2025-04-02 | 4
|  |  | 15 | 2d |  | 2025-04-02 | 5
|  |  | 30 | 2e |  | 2025-04-02 | 6
| 1 | 0.03 | 0 | 3b |  | 2025-04-02 | 7
|  |  | 15 | 3d |  | 2025-04-02 | 8
|  |  | 30 | 3e |  | 2025-04-02 | 9
| 1.33 | 0.03 | 0 | 1b_ex |  | 2025-04-02 | 10
| 1.25 | 0.03 | 0 | 2b_ex |  | 2025-04-02 | 11
Test Description | Random Wave Input | Directional Spreading [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | JONSWAP (represent North Atlantic) NOAA Buoy Station 44011 gamma = 1.54 Hs = 0.020 m Tp = 1.56 s (0.643 Hz) Period Range: as much as we can generate | 15 | Ran2a | 6 | 2025-04-02 | 1
|  | 30 | Ran2b |  | 2025-04-02 | 2
|  | 45 | Ran2c |  | 2025-04-02 | 3
| JONSWAP (represent Pacific Northwest) NOAA Buoy 46229 SCRIPPS gamma = 2 Hs = 0.073 m Tp = 2.12 s (0.471 Hz) Period Range: as much as we can generate | 15 | Ran3a | 10 | 2025-04-02 | 4
|  | 30 | Ran3b |  | 2025-04-02 | 5
|  | 45 | Ran3c |  | 2025-04-02 | 6

## OSWEC
Test Description | Period(s) [s] | Amplitude(s) [m] | Wave Heading(s) [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | 1.39 | 0.03 | 0 | 1b | 2 | 2025-04-03 | 1
|  |  | 15 | 1d |  | 2025-04-03 | 2
|  |  | 30 | 1e |  | 2025-04-03 | 3
| 1.2 | 0.03 | 0 | 2b |  | 2025-04-03 | 4
|  |  | 15 | 2d |  | 2025-04-03 | 5
|  |  | 30 | 2e |  | 2025-04-03 | 6
| 1 | 0.03 | 0 | 3b |  | 2025-04-03 | 7
|  |  | 15 | 3d |  | 2025-04-03 | 8
|  |  | 30 | 3e |  | 2025-04-03 | 9
| 1.33 | 0.03 | 0 | 1b_ex |  | 2025-04-03 | 10
| 1.25 | 0.03 | 0 | 2b_ex |  | 2025-04-03 | 11
| 1.33 | 0.13 | 0 | fun |  | 2025-04-03 | 12
Test Description | Random Wave Input | Directional Spreading [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | JONSWAP (represent North Atlantic) NOAA Buoy Station 44011 gamma = 1.54 Hs = 0.020 m Tp = 1.56 s (0.643 Hz) Period Range: as much as we can generate | 15 | Ran2a | 6 | 2025-04-03 | 1
|  | 30 | Ran2b |  | 2025-04-03 | 2
|  | 45 | Ran2c |  | 2025-04-03 | 3
| JONSWAP (represent Pacific Northwest) NOAA Buoy 46229 SCRIPPS gamma = 2 Hs = 0.073 m Tp = 2.12 s (0.471 Hz) Period Range: as much as we can generate | 15 | Ran3a | 10 | 2025-04-03 | 4
|  | 30 | Ran3b |  | 2025-04-03 | 5
|  | 45 | Ran3c |  | 2025-04-03 | 6
Test Description | Trial Number | Date
Free Decay Push the device with the long stick | 1 | 2025-04-03
| 2 | 2025-04-03
| 3 | 2025-04-03

## PA
Test Description | Period(s) [s] | Amplitude(s) [m] | Wave Heading(s) [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | 1.39 | 0.03 | 0 | 1b | 2 | 2025-04-04 | 1
|  |  | 15 | 1d |  | 2025-04-04 | 2
|  |  | 30 | 1e |  | 2025-04-04 | 3
| 1.2 | 0.03 | 0 | 2b |  | 2025-04-04 | 4
|  |  | 15 | 2d |  | 2025-04-04 | 5
|  |  | 30 | 2e |  | 2025-04-04 | 6
| 1 | 0.03 | 0 | 3b |  | 2025-04-04 | 7
|  |  | 15 | 3d |  | 2025-04-04 | 8
|  |  | 30 | 3e |  | 2025-04-04 | 9
| 1.33 | 0.03 | 0 | 1b_ex |  | 2025-04-04 | 10
| 1.25 | 0.03 | 0 | 2b_ex |  | 2025-04-04 | 11
| 1.33 | 0.13 | 0 | fun |  | 2025-04-04 | 12
Test Description | Random Wave Input | Directional Spreading [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | JONSWAP (represent North Atlantic) NOAA Buoy Station 44011 gamma = 1.54 Hs = 0.020 m Tp = 1.56 s (0.643 Hz) Period Range: as much as we can generate | 15 | Ran2a | 6 | 2025-04-04 | 1
|  | 30 | Ran2b |  | 2025-04-04 | 2
|  | 45 | Ran2c |  | 2025-04-04 | 3
| JONSWAP (represent Pacific Northwest) NOAA Buoy 46229 SCRIPPS gamma = 2 Hs = 0.073 m Tp = 2.12 s (0.471 Hz) Period Range: as much as we can generate | 15 | Ran3a | 10 | 2025-04-04 | 4
|  | 30 | Ran3b |  | 2025-04-04 | 5
|  | 45 | Ran3c |  | 2025-04-04 | 6
Test Description | Date | Trial Number
Free Decay Push the device with the long stick (we pushed for some trials and lifted from the bottom for some) | 2025-04-04 | 7 total trials

## Daily Goals
2025-04-01 | Set up het 5a config
| Three OSWECs and two PAs | TRUE
| Fill tank | TRUE
2025-04-02 | Complete wave tests
| Tests 1b, 1d, 1e, 2b, 2d, 2e, 3b, 3d, 3e, 1b_ex, 2b_ex (11 tests) | TRUE
| Tests Ran2a through Ran3c, 6 tests total | TRUE
| Remove all floats but one OSWEC | TRUE
2025-04-03 | Single body wave tests
| Tests 1b, 1d, 1e, 2b, 2d, 2e, 3b, 3d, 3e, 1b_ex, 2b_ex (11 tests) | TRUE
| Tests Ran2a through Ran3c, 6 tests total | TRUE
| Free decay | TRUE
| Remove OSWEC, place a PA | TRUE
2025-04-04 | Complete single body wave tests
| Tests 1b, 1d, 1e, 2b, 2d, 2e, 3b, 3d, 3e, 1b_ex, 2b_ex (11 tests) | TRUE
| Finalize shipping details | TRUE
| Tests Ran2a through Ran3c, 6 tests total | TRUE
| Free decay | TRUE
| Drain tank | TRUE
weekend
2025-04-07 | Tear down
| disassemble everything | TRUE
| pack everything | TRUE
2025-04-08 | Complete tear down
| ship boxes | TRUE
2025-04-09 | Olivia flies out