## OS Waves
Test Description | Period(s) [s] | Amplitude(s) [m] | Wave Heading(s) [deg] | Test Number | Duration [min] | Date | Trial Number | Project Folder: 20250327_Regular_WaveExcitation
Body motion, power production (PTO disengaged) | 1.39 | 0.03 | 0 | 1b | 2 | 2025-03-27 | 1 and 10
|  |  | 15 | 1d |  | 2025-03-27 | 2
|  |  | 30 | 1e |  | 2025-03-27 | 3
| 1.2 | 0.03 | 0 | 2b |  | 2025-03-27 | 4
|  |  | 15 | 2d |  | 2025-03-27 | 5
|  |  | 30 | 2e |  | 2025-03-27 | 6
| 1 | 0.03 | 0 | 3b |  | 2025-03-27 | 7
|  |  | 15 | 3d |  | 2025-03-27 | 8
|  |  | 30 | 3e |  | 2025-03-27 | 9
| 1.33 | 0.03 | 0 | 1b_ex |  | 2025-03-27 | 11
| 1.25 | 0.03 | 0 | 2b_ex |  | 2025-03-27 | 12
Test Description | Random Wave Input | Directional Spreading [deg] | Test Number | Duration [min] | Date | Trial Number | Project Folder: 20250327_Random_WaveExcitation
Body motion, power production (PTO disengaged) | JONSWAP (represent North Atlantic) NOAA Buoy Station 44011 gamma = 1.54 Hs = 0.020 m Tp = 1.56 s (0.643 Hz) Period Range: as much as we can generate | 15 | Ran2a | 6 | 2025-03-27 | 1
|  | 30 | Ran2b |  | 2025-03-27 | 2
|  | 45 | Ran2c |  | 2025-03-27 | 3
| JONSWAP (represent Pacific Northwest) NOAA Buoy 46229 SCRIPPS gamma = 2 Hs = 0.073 m Tp = 2.12 s (0.471 Hz) Period Range: as much as we can generate | 15 | Ran3a | 10 | 2025-03-27 | 4
|  | 30 | Ran3b |  | 2025-03-27 | 5
|  | 45 | Ran3c |  | 2025-03-27 | 6

## PA Waves
Test Description | Period(s) [s] | Amplitude(s) [m] | Wave Heading(s) [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | 1.39 | 0.03 | 0 | 1b | 2 | 2025-03-31 | 1 & 12
|  |  | 15 | 1d |  | 2025-03-31 | 2
|  |  | 30 | 1e |  | 2025-03-31 | 3
| 1.2 | 0.03 | 0 | 2b |  | 2025-03-31 | 4
|  |  | 15 | 2d |  | 2025-03-31 | 5
|  |  | 30 | 2e |  | 2025-03-31 | 6
| 1 | 0.03 | 0 | 3b |  | 2025-03-31 | 7
|  |  | 15 | 3d |  | 2025-03-31 | 8
|  |  | 30 | 3e |  | 2025-03-31 | 9
| 1.33 | 0.03 | 0 | 1b_ex |  | 2025-03-31 | 10
| 1.25 | 0.03 | 0 | 2b_ex |  | 2025-03-31 | 11
Test Description | Random Wave Input | Directional Spreading [deg] | Test Number | Duration [min] | Date | Trial Number
Body motion, power production (PTO disengaged) | JONSWAP (represent North Atlantic) NOAA Buoy Station 44011 gamma = 1.54 Hs = 0.020 m Tp = 1.56 s (0.643 Hz) Period Range: as much as we can generate | 15 | Ran2a | 6 | 2025-03-31 | 1
|  | 30 | Ran2b |  | 2025-03-31 | 2
|  | 45 | Ran2c |  | 2025-03-31 | 3
| JONSWAP (represent Pacific Northwest) NOAA Buoy 46229 SCRIPPS gamma = 2 Hs = 0.073 m Tp = 2.12 s (0.471 Hz) Period Range: as much as we can generate | 15 | Ran3a | 10 | 2025-03-31 | 4
|  | 30 | Ran3b |  | 2025-03-31 | 5
|  | 45 | Ran3c |  | 2025-03-31 | 6

## Daily Goals
2025-03-26 | Set up hom OSWEC 4b config
| Swap out PAs for OSWECs | TRUE
| Re-secure mooring, remove middle bars between Eloise and Greta | TRUE
| Attach motor housings | TRUE
| Place MoCap balls | TRUE
| Fill tank | TRUE
2025-03-27 | Complete wave tests
| Tests 1b, 1d, 1e, 2b, 2d, 2e, 3b, 3d, 3e (9 tests) | TRUE
| Tests Ran2a through Ran3c, 6 tests total | TRUE
| drain tank | TRUE
2025-03-28 | Set up hom 4b PA config
| Swap out all OSWECs for all PAs (oof) | TRUE
| Fill tank | TRUE
weekend
2025-03-31 | Complete wave tests
| Tests 1b, 1d, 1e, 2b, 2d, 2e, 3b, 3d, 3e, 1b_ex, 2b_ex (11 tests) | TRUE
| Tests Ran2a through Ran3c, 6 tests total | TRUE
| Drain tank | TRUE